## Overview
DreamDrive microservices — Backend / Frontend tracker
MVP 13 Aug – 9 Sep 2026 · Edit Status or Layer on All Tasks. Backend + Frontend sheets are 4-column boards. · Current week: Week 1
| Backend tasks |  | Backend completed |  | Frontend tasks |  | Frontend completed
| Not started |  | In progress |  | Under review |  | Completed
Backend vs Frontend by week
Week | Dates | BE tasks | BE done | FE tasks | FE done | Ships
Week 1 | 13–19 Aug 2026 |  |  |  |  | Auth, cities, car models, admin login
Week 2 | 20–26 Aug 2026 |  |  |  |  | Availability, HOLD, Razorpay token
Week 3 | 27 Aug–2 Sep 2026 |  |  |  |  | KYC, Zoho, Leegality, confirm email
Week 4 | 3–9 Sep 2026 |  |  |  |  | Handover, drivers, CMS, staging demo
Later | After 9 Sep 2026 |  |  |  |  | Subscription, workshop, partners, wallet, GST, mobile
Status by module (Backend / Frontend)
Module | BE | BE done | FE | FE done | Not started | In progress | Under review | Completed
Foundation
Auth
CMS
Dashboard
Search
Booking
Payments
Subscription
Airport
KYC
E-sign
Fleet
Workshop
Handover
Drivers
Partners
Admin
Finance
Offers
Reviews
Notify
CRM
Mobile
How to use
Backend = NestJS services, Prisma, gateway, webhooks. Frontend = Next.js web, Next.js admin, Expo mobile. Open the Backend or Frontend tab for a 4-column board. Module tabs still exist. Change Status on All Tasks — counts update.

## All Tasks
ID | Layer | Module | Service | Task | Week | Week dates | Status
f1 | Backend | Foundation | gateway, infra, web, admin | Monorepo, turbo, Nest service packages | Week 1 | 13–19 Aug 2026 | Completed
f2 | Backend | Foundation | gateway, infra, web, admin | Docker Compose Postgres + Redis | Week 1 | 13–19 Aug 2026 | Completed
f3 | Backend | Foundation | gateway, infra, web, admin | Prisma schema draft (all domains) | Week 1 | 13–19 Aug 2026 | Under review
f4 | Backend | Foundation | gateway, infra, web, admin | NestJS service stubs + health | Week 1 | 13–19 Aug 2026 | Completed
f5 | Backend | Foundation | gateway, infra, web, admin | Prisma migrate on local Docker | Week 1 | 13–19 Aug 2026 | Not started
f6 | Backend | Foundation | gateway, infra, web, admin | Gateway Firebase JWT verify + /v1 proxy | Week 1 | 13–19 Aug 2026 | Not started
f7 | Backend | Foundation | gateway, infra, web, admin | Shared env + service ports | Week 1 | 13–19 Aug 2026 | Not started
f8 | Backend | Foundation | gateway, infra, web, admin | Rate limits, audit, staging API deploy | Week 4 | 3–9 Sep 2026 | Not started
ff1 | Frontend | Foundation | gateway, infra, web, admin | Next.js web + admin package stubs | Week 1 | 13–19 Aug 2026 | Completed
ff2 | Frontend | Foundation | gateway, infra, web, admin | Web/admin Tailwind + shadcn shells | Week 1 | 13–19 Aug 2026 | Not started
ff3 | Frontend | Foundation | gateway, infra, web, admin | Wire apps to gateway API base URL | Week 1 | 13–19 Aug 2026 | Not started
ff4 | Frontend | Foundation | gateway, infra, web, admin | Web + admin staging deploy | Week 4 | 3–9 Sep 2026 | Not started
a1 | Backend | Auth | identity | Auth API + RBAC spec | Week 1 | 13–19 Aug 2026 | Completed
a2 | Backend | Auth | identity | Identity Nest stub | Week 1 | 13–19 Aug 2026 | Completed
a3 | Backend | Auth | identity | POST /v1/auth/sync from Firebase token | Week 1 | 13–19 Aug 2026 | Not started
a4 | Backend | Auth | identity | GET/PATCH /v1/me + roles | Week 1 | 13–19 Aug 2026 | Not started
a5 | Backend | Auth | identity | Invite staff, assign roles, disable APIs | Week 1 | 13–19 Aug 2026 | Not started
a6 | Backend | Auth | identity | Audit log for privileged writes | Week 4 | 3–9 Sep 2026 | Not started
af1 | Frontend | Auth | identity | Web login / signup + OTP verify UI | Week 1 | 13–19 Aug 2026 | Not started
af2 | Frontend | Auth | identity | Admin login (Firebase) | Week 1 | 13–19 Aug 2026 | Not started
c1 | Backend | CMS | platform | CMS API spec | Week 4 | 3–9 Sep 2026 | Completed
c2 | Backend | CMS | platform | Public pages, banners, blogs APIs | Week 4 | 3–9 Sep 2026 | Not started
c3 | Backend | CMS | platform | Admin CMS CRUD + publish APIs | Week 4 | 3–9 Sep 2026 | Not started
cf1 | Frontend | CMS | platform | Web home banners, blogs, contact page | Week 4 | 3–9 Sep 2026 | Not started
cf2 | Frontend | CMS | platform | Admin CMS screens | Week 4 | 3–9 Sep 2026 | Not started
d1 | Backend | Dashboard | identity, web | Customer account API spec | Week 1 | 13–19 Aug 2026 | Completed
d2 | Backend | Dashboard | identity, web | Customer bookings + profile APIs | Week 2 | 20–26 Aug 2026 | Not started
df1 | Frontend | Dashboard | identity, web | Web account shell | Week 1 | 13–19 Aug 2026 | Not started
df2 | Frontend | Dashboard | identity, web | Customer bookings list UI | Week 2 | 20–26 Aug 2026 | Not started
df3 | Frontend | Dashboard | identity, web | Tracking page after confirm | Week 3 | 27 Aug–2 Sep 2026 | Not started
s1 | Backend | Search | catalog | Search / catalog API spec | Week 1 | 13–19 Aug 2026 | Completed
s2 | Backend | Search | catalog | Catalog Nest stub | Week 1 | 13–19 Aug 2026 | Completed
s3 | Backend | Search | catalog | CarModel CRUD APIs | Week 1 | 13–19 Aug 2026 | Not started
s4 | Backend | Search | catalog | Availability engine + buffer hours | Week 2 | 20–26 Aug 2026 | Not started
s5 | Backend | Search | catalog | Maintenance block stub on calendar | Week 2 | 20–26 Aug 2026 | Not started
sf1 | Frontend | Search | catalog | Public car list + search UI | Week 1 | 13–19 Aug 2026 | Not started
sf2 | Frontend | Search | catalog | Availability calendar on car page | Week 2 | 20–26 Aug 2026 | Not started
b1 | Backend | Booking | booking | Booking API spec | Week 2 | 20–26 Aug 2026 | Completed
b2 | Backend | Booking | booking | Booking Nest stub | Week 2 | 20–26 Aug 2026 | Completed
b3 | Backend | Booking | booking | Quote freeze + HOLD (15 min) API | Week 2 | 20–26 Aug 2026 | Not started
b4 | Backend | Booking | booking | Status machine through CONFIRMED | Week 3 | 27 Aug–2 Sep 2026 | Not started
b5 | Backend | Booking | booking | Admin bookings list API + filters | Week 2 | 20–26 Aug 2026 | Not started
b6 | Backend | Booking | booking | Assign vehicle/driver API | Week 4 | 3–9 Sep 2026 | Not started
bf1 | Frontend | Booking | booking | Web checkout: quote → hold → pay | Week 2 | 20–26 Aug 2026 | Not started
bf2 | Frontend | Booking | booking | Admin bookings list screens | Week 2 | 20–26 Aug 2026 | Not started
bf3 | Frontend | Booking | booking | Admin assign vehicle/driver UI | Week 4 | 3–9 Sep 2026 | Not started
p1 | Backend | Payments | payment | Payments API spec | Week 2 | 20–26 Aug 2026 | Completed
p2 | Backend | Payments | payment | Payment Nest stub | Week 2 | 20–26 Aug 2026 | Completed
p3 | Backend | Payments | payment | Razorpay order + webhook (idempotent) | Week 2 | 20–26 Aug 2026 | Not started
p4 | Backend | Payments | payment | Token invoice + verify APIs | Week 2 | 20–26 Aug 2026 | Not started
p5 | Backend | Payments | payment | Refund path for cancel before handover | Week 4 | 3–9 Sep 2026 | Not started
pf1 | Frontend | Payments | payment | Checkout pay + success poll UI | Week 2 | 20–26 Aug 2026 | Not started
sub1 | Backend | Subscription | booking | Subscription API spec | Later | After 9 Sep 2026 | Completed
sub2 | Backend | Subscription | booking | Plans + tenure booking APIs | Later | After 9 Sep 2026 | Not started
sub3 | Backend | Subscription | booking | Swap / early close policy APIs | Later | After 9 Sep 2026 | Not started
subf1 | Frontend | Subscription | booking | Subscription plans + checkout UI | Later | After 9 Sep 2026 | Not started
air1 | Backend | Airport | booking | Airport / outstation API spec | Week 4 | 3–9 Sep 2026 | Completed
air2 | Backend | Airport | booking | Airport / one-way rate table APIs | Week 4 | 3–9 Sep 2026 | Not started
air3 | Backend | Airport | booking | Tour package APIs | Later | After 9 Sep 2026 | Not started
airf1 | Frontend | Airport | booking | Airport / one-way search options UI | Week 4 | 3–9 Sep 2026 | Not started
k1 | Backend | KYC | document | KYC API spec | Week 3 | 27 Aug–2 Sep 2026 | Completed
k2 | Backend | KYC | document | Document Nest stub | Week 3 | 27 Aug–2 Sep 2026 | Completed
k3 | Backend | KYC | document | Upload + admin approve/reject APIs | Week 3 | 27 Aug–2 Sep 2026 | Not started
k4 | Backend | KYC | document | Gate booking on AWAITING_KYC | Week 3 | 27 Aug–2 Sep 2026 | Not started
kf1 | Frontend | KYC | document | Customer KYC upload UI | Week 3 | 27 Aug–2 Sep 2026 | Not started
kf2 | Frontend | KYC | document | Admin KYC review screens | Week 3 | 27 Aug–2 Sep 2026 | Not started
e1 | Backend | E-sign | document | E-sign API spec | Week 3 | 27 Aug–2 Sep 2026 | Completed
e2 | Backend | E-sign | document | Agreement PDF from booking snapshot | Week 3 | 27 Aug–2 Sep 2026 | Not started
e3 | Backend | E-sign | document | Leegality send + webhook | Week 3 | 27 Aug–2 Sep 2026 | Not started
e4 | Backend | E-sign | document | Advance to CONFIRMED after sign | Week 3 | 27 Aug–2 Sep 2026 | Not started
ef1 | Frontend | E-sign | document | Customer sign / status page | Week 3 | 27 Aug–2 Sep 2026 | Not started
fl1 | Backend | Fleet | fleet | Fleet API spec | Week 1 | 13–19 Aug 2026 | Completed
fl2 | Backend | Fleet | fleet | Fleet Nest stub | Week 1 | 13–19 Aug 2026 | Completed
fl3 | Backend | Fleet | fleet | City, Branch, Vehicle APIs | Week 1 | 13–19 Aug 2026 | Not started
fl5 | Backend | Fleet | fleet | Assign vehicle to confirmed booking API | Week 4 | 3–9 Sep 2026 | Not started
flf1 | Frontend | Fleet | fleet | Admin cars + vehicles CRUD screens | Week 1 | 13–19 Aug 2026 | Not started
m1 | Backend | Workshop | fleet | Workshop API spec | Later | After 9 Sep 2026 | Completed
m2 | Backend | Workshop | fleet | Jobs + workshop calendar APIs | Later | After 9 Sep 2026 | Not started
m3 | Backend | Workshop | fleet | Write AvailabilityBlock on schedule | Later | After 9 Sep 2026 | Not started
mf1 | Frontend | Workshop | fleet | Admin workshop screens | Later | After 9 Sep 2026 | Not started
h1 | Backend | Handover | fleet | Handover API spec | Week 4 | 3–9 Sep 2026 | Completed
h2 | Backend | Handover | fleet | Handover API: odometer + photos | Week 4 | 3–9 Sep 2026 | Not started
h3 | Backend | Handover | fleet | Return + close booking API | Week 4 | 3–9 Sep 2026 | Not started
hf1 | Frontend | Handover | fleet | Admin handover / return screens | Week 4 | 3–9 Sep 2026 | Not started
dr1 | Backend | Drivers | fleet | Drivers API spec | Week 4 | 3–9 Sep 2026 | Completed
dr2 | Backend | Drivers | fleet | Driver roster + assign APIs | Week 4 | 3–9 Sep 2026 | Not started
drf1 | Frontend | Drivers | fleet | Admin driver roster screens | Week 4 | 3–9 Sep 2026 | Not started
pt1 | Backend | Partners | partner | Partners API spec | Later | After 9 Sep 2026 | Completed
pt2 | Backend | Partners | partner | Partner cars + commission ledger APIs | Later | After 9 Sep 2026 | Not started
pt3 | Backend | Partners | partner | Settlements APIs (no partner portal) | Later | After 9 Sep 2026 | Not started
ptf1 | Frontend | Partners | partner | Admin partner + settlement screens | Later | After 9 Sep 2026 | Not started
ad1 | Backend | Admin | platform, fleet | Admin / multi-city spec | Week 1 | 13–19 Aug 2026 | Completed
ad4b | Backend | Admin | platform, fleet | Dashboard KPI APIs | Week 4 | 3–9 Sep 2026 | Not started
ad5 | Backend | Admin | platform, fleet | City / branch scoped RBAC on APIs | Week 4 | 3–9 Sep 2026 | Not started
adf1 | Frontend | Admin | platform, fleet | Admin app shell + nav | Week 1 | 13–19 Aug 2026 | Not started
adf2 | Frontend | Admin | platform, fleet | Staff, cars, vehicles screens | Week 1 | 13–19 Aug 2026 | Not started
adf3 | Frontend | Admin | platform, fleet | Dashboard KPI screens | Week 4 | 3–9 Sep 2026 | Not started
adf4 | Frontend | Admin | platform, fleet | City / branch scoped nav + filters | Week 4 | 3–9 Sep 2026 | Not started
fn1 | Backend | Finance | platform | Finance API spec | Later | After 9 Sep 2026 | Completed
fn2 | Backend | Finance | platform | Revenue / deposits / GST report APIs | Later | After 9 Sep 2026 | Not started
fnf1 | Frontend | Finance | platform | Admin finance report screens | Later | After 9 Sep 2026 | Not started
o1 | Backend | Offers | platform | Offers API spec | Week 2 | 20–26 Aug 2026 | Completed
o2 | Backend | Offers | platform | Flat / percent offer code APIs | Week 2 | 20–26 Aug 2026 | Not started
o3 | Backend | Offers | platform | Wallet + loyalty APIs | Later | After 9 Sep 2026 | Not started
of1 | Frontend | Offers | platform | Checkout apply offer code UI | Week 2 | 20–26 Aug 2026 | Not started
of2 | Frontend | Offers | platform | Admin offers screens | Week 2 | 20–26 Aug 2026 | Not started
r1 | Backend | Reviews | platform | Reviews API spec | Later | After 9 Sep 2026 | Completed
r2 | Backend | Reviews | platform | Review invite + ticket APIs | Later | After 9 Sep 2026 | Not started
rf1 | Frontend | Reviews | platform | Post-trip review + support UI | Later | After 9 Sep 2026 | Not started
n1 | Backend | Notify | notification | Notifications API spec | Week 1 | 13–19 Aug 2026 | Completed
n2 | Backend | Notify | notification | Notification Nest stub | Week 1 | 13–19 Aug 2026 | Completed
n3 | Backend | Notify | notification | OTP email (port Gmail OAuth) | Week 1 | 13–19 Aug 2026 | Not started
n4 | Backend | Notify | notification | Booking confirmation HTML email | Week 3 | 27 Aug–2 Sep 2026 | Not started
cr1 | Backend | CRM | platform | CRM API spec | Week 3 | 27 Aug–2 Sep 2026 | Completed
cr2 | Backend | CRM | platform | Zoho form webhook → lead | Week 3 | 27 Aug–2 Sep 2026 | Not started
cr3 | Backend | CRM | platform | Contact form → CRM lead API | Week 4 | 3–9 Sep 2026 | Not started
crf1 | Frontend | CRM | platform | Admin leads list screens | Week 4 | 3–9 Sep 2026 | Not started
mb1 | Frontend | Mobile | apps/mobile | Mobile spec | Later | After 9 Sep 2026 | Completed
mb2 | Frontend | Mobile | apps/mobile | Expo app: search, book, track | Later | After 9 Sep 2026 | Not started

## Timeline
4-week timeline · Backend vs Frontend · 13 Aug – 9 Sep 2026
Backend (NestJS, Prisma, gateway)
Workstream | Week 1 13–19 Aug | Week 2 20–26 Aug | Week 3 27 Aug–2 Sep | Week 4 3–9 Sep
Gateway / infra | ●
Identity APIs | ●
Fleet APIs | ●
OTP email | ●
Catalog / availability | ● | ●
Booking engine |  | ● | ●
Razorpay |  | ●
KYC APIs |  |  | ●
Leegality |  |  | ●
Zoho webhook |  |  | ● | ●
Handover APIs |  |  |  | ●
Frontend (Next.js web, admin, Expo)
Workstream | Week 1 13–19 Aug | Week 2 20–26 Aug | Week 3 27 Aug–2 Sep | Week 4 3–9 Sep
Web + admin shells | ●
Login + car list | ●
Checkout + pay UI |  | ●
Tracking + KYC UI |  |  | ●
Admin bookings / assign |  | ● | ● | ●
CMS + handover UI |  |  |  | ●
Shaded bar = planned that week. Week 1 column is current. Later work is on All Tasks filtered to Later.

## Backend
Backend board · 31 of 81 completed
NestJS / Prisma / gateway
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Module | Task | Week | Module | Task | Week | Module | Task | Week | Module | Task
Week 1 | Foundation | Prisma migrate on local Docker |  |  |  | Week 1 | Foundation | Prisma schema draft (all domains) | Week 1 | Foundation | Monorepo, turbo, Nest service packages
Week 1 | Foundation | Gateway Firebase JWT verify + /v1 proxy | [6 empty] | Week 1 | Foundation | Docker Compose Postgres + Redis
Week 1 | Foundation | Shared env + service ports | [6 empty] | Week 1 | Foundation | NestJS service stubs + health
Week 4 | Foundation | Rate limits, audit, staging API deploy | [6 empty] | Week 1 | Auth | Auth API + RBAC spec
Week 1 | Auth | POST /v1/auth/sync from Firebase token | [6 empty] | Week 1 | Auth | Identity Nest stub
Week 1 | Auth | GET/PATCH /v1/me + roles | [6 empty] | Week 4 | CMS | CMS API spec
Week 1 | Auth | Invite staff, assign roles, disable APIs | [6 empty] | Week 1 | Dashboard | Customer account API spec
Week 4 | Auth | Audit log for privileged writes | [6 empty] | Week 1 | Search | Search / catalog API spec
Week 4 | CMS | Public pages, banners, blogs APIs | [6 empty] | Week 1 | Search | Catalog Nest stub
Week 4 | CMS | Admin CMS CRUD + publish APIs | [6 empty] | Week 2 | Booking | Booking API spec
Week 2 | Dashboard | Customer bookings + profile APIs | [6 empty] | Week 2 | Booking | Booking Nest stub
Week 1 | Search | CarModel CRUD APIs | [6 empty] | Week 2 | Payments | Payments API spec
Week 2 | Search | Availability engine + buffer hours | [6 empty] | Week 2 | Payments | Payment Nest stub
Week 2 | Search | Maintenance block stub on calendar | [6 empty] | Later | Subscription | Subscription API spec
Week 2 | Booking | Quote freeze + HOLD (15 min) API | [6 empty] | Week 4 | Airport | Airport / outstation API spec
Week 3 | Booking | Status machine through CONFIRMED | [6 empty] | Week 3 | KYC | KYC API spec
Week 2 | Booking | Admin bookings list API + filters | [6 empty] | Week 3 | KYC | Document Nest stub
Week 4 | Booking | Assign vehicle/driver API | [6 empty] | Week 3 | E-sign | E-sign API spec
Week 2 | Payments | Razorpay order + webhook (idempotent) | [6 empty] | Week 1 | Fleet | Fleet API spec
Week 2 | Payments | Token invoice + verify APIs | [6 empty] | Week 1 | Fleet | Fleet Nest stub
Week 4 | Payments | Refund path for cancel before handover | [6 empty] | Later | Workshop | Workshop API spec
Later | Subscription | Plans + tenure booking APIs | [6 empty] | Week 4 | Handover | Handover API spec
Later | Subscription | Swap / early close policy APIs | [6 empty] | Week 4 | Drivers | Drivers API spec
Week 4 | Airport | Airport / one-way rate table APIs | [6 empty] | Later | Partners | Partners API spec
Later | Airport | Tour package APIs | [6 empty] | Week 1 | Admin | Admin / multi-city spec
Week 3 | KYC | Upload + admin approve/reject APIs | [6 empty] | Later | Finance | Finance API spec
Week 3 | KYC | Gate booking on AWAITING_KYC | [6 empty] | Week 2 | Offers | Offers API spec
Week 3 | E-sign | Agreement PDF from booking snapshot | [6 empty] | Later | Reviews | Reviews API spec
Week 3 | E-sign | Leegality send + webhook | [6 empty] | Week 1 | Notify | Notifications API spec
Week 3 | E-sign | Advance to CONFIRMED after sign | [6 empty] | Week 1 | Notify | Notification Nest stub
Week 1 | Fleet | City, Branch, Vehicle APIs | [6 empty] | Week 3 | CRM | CRM API spec
Week 4 | Fleet | Assign vehicle to confirmed booking API
Later | Workshop | Jobs + workshop calendar APIs
Later | Workshop | Write AvailabilityBlock on schedule
Week 4 | Handover | Handover API: odometer + photos
Week 4 | Handover | Return + close booking API
Week 4 | Drivers | Driver roster + assign APIs
Later | Partners | Partner cars + commission ledger APIs
Later | Partners | Settlements APIs (no partner portal)
Week 4 | Admin | Dashboard KPI APIs
Week 4 | Admin | City / branch scoped RBAC on APIs
Later | Finance | Revenue / deposits / GST report APIs
Week 2 | Offers | Flat / percent offer code APIs
Later | Offers | Wallet + loyalty APIs
Later | Reviews | Review invite + ticket APIs
Week 1 | Notify | OTP email (port Gmail OAuth)
Week 3 | Notify | Booking confirmation HTML email
Week 3 | CRM | Zoho form webhook → lead
Week 4 | CRM | Contact form → CRM lead API

## Frontend
Frontend board · 2 of 38 completed
Next.js web, Next.js admin, Expo mobile
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Module | Task | Week | Module | Task | Week | Module | Task | Week | Module | Task
Week 1 | Foundation | Web/admin Tailwind + shadcn shells | [6 empty] | Week 1 | Foundation | Next.js web + admin package stubs
Week 1 | Foundation | Wire apps to gateway API base URL | [6 empty] | Later | Mobile | Mobile spec
Week 4 | Foundation | Web + admin staging deploy
Week 1 | Auth | Web login / signup + OTP verify UI
Week 1 | Auth | Admin login (Firebase)
Week 4 | CMS | Web home banners, blogs, contact page
Week 4 | CMS | Admin CMS screens
Week 1 | Dashboard | Web account shell
Week 2 | Dashboard | Customer bookings list UI
Week 3 | Dashboard | Tracking page after confirm
Week 1 | Search | Public car list + search UI
Week 2 | Search | Availability calendar on car page
Week 2 | Booking | Web checkout: quote → hold → pay
Week 2 | Booking | Admin bookings list screens
Week 4 | Booking | Admin assign vehicle/driver UI
Week 2 | Payments | Checkout pay + success poll UI
Later | Subscription | Subscription plans + checkout UI
Week 4 | Airport | Airport / one-way search options UI
Week 3 | KYC | Customer KYC upload UI
Week 3 | KYC | Admin KYC review screens
Week 3 | E-sign | Customer sign / status page
Week 1 | Fleet | Admin cars + vehicles CRUD screens
Later | Workshop | Admin workshop screens
Week 4 | Handover | Admin handover / return screens
Week 4 | Drivers | Admin driver roster screens
Later | Partners | Admin partner + settlement screens
Week 1 | Admin | Admin app shell + nav
Week 1 | Admin | Staff, cars, vehicles screens
Week 4 | Admin | Dashboard KPI screens
Week 4 | Admin | City / branch scoped nav + filters
Later | Finance | Admin finance report screens
Week 2 | Offers | Checkout apply offer code UI
Week 2 | Offers | Admin offers screens
Later | Reviews | Post-trip review + support UI
Week 4 | CRM | Admin leads list screens
Later | Mobile | Expo app: search, book, track

## Foundation
Foundation · gateway, infra, web, admin · 8 backend / 4 frontend · 4/12 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 1 | Backend | Prisma migrate on local Docker |  |  |  | Week 1 | Backend | Prisma schema draft (all domains) | Week 1 | Backend | Monorepo, turbo, Nest service packages
Week 1 | Backend | Gateway Firebase JWT verify + /v1 proxy | [6 empty] | Week 1 | Backend | Docker Compose Postgres + Redis
Week 1 | Backend | Shared env + service ports | [6 empty] | Week 1 | Backend | NestJS service stubs + health
Week 4 | Backend | Rate limits, audit, staging API deploy | [6 empty] | Week 1 | Frontend | Next.js web + admin package stubs
Week 1 | Frontend | Web/admin Tailwind + shadcn shells
Week 1 | Frontend | Wire apps to gateway API base URL
Week 4 | Frontend | Web + admin staging deploy

## Auth
Auth · identity · 6 backend / 2 frontend · 2/8 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 1 | Backend | POST /v1/auth/sync from Firebase token | [6 empty] | Week 1 | Backend | Auth API + RBAC spec
Week 1 | Backend | GET/PATCH /v1/me + roles | [6 empty] | Week 1 | Backend | Identity Nest stub
Week 1 | Backend | Invite staff, assign roles, disable APIs
Week 4 | Backend | Audit log for privileged writes
Week 1 | Frontend | Web login / signup + OTP verify UI
Week 1 | Frontend | Admin login (Firebase)

## CMS
CMS · platform · 3 backend / 2 frontend · 1/5 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 4 | Backend | Public pages, banners, blogs APIs | [6 empty] | Week 4 | Backend | CMS API spec
Week 4 | Backend | Admin CMS CRUD + publish APIs
Week 4 | Frontend | Web home banners, blogs, contact page
Week 4 | Frontend | Admin CMS screens

## Dashboard
Dashboard · identity, web · 2 backend / 3 frontend · 1/5 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 2 | Backend | Customer bookings + profile APIs | [6 empty] | Week 1 | Backend | Customer account API spec
Week 1 | Frontend | Web account shell
Week 2 | Frontend | Customer bookings list UI
Week 3 | Frontend | Tracking page after confirm

## Search
Search · catalog · 5 backend / 2 frontend · 2/7 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 1 | Backend | CarModel CRUD APIs | [6 empty] | Week 1 | Backend | Search / catalog API spec
Week 2 | Backend | Availability engine + buffer hours | [6 empty] | Week 1 | Backend | Catalog Nest stub
Week 2 | Backend | Maintenance block stub on calendar
Week 1 | Frontend | Public car list + search UI
Week 2 | Frontend | Availability calendar on car page

## Booking
Booking · booking · 6 backend / 3 frontend · 2/9 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 2 | Backend | Quote freeze + HOLD (15 min) API | [6 empty] | Week 2 | Backend | Booking API spec
Week 3 | Backend | Status machine through CONFIRMED | [6 empty] | Week 2 | Backend | Booking Nest stub
Week 2 | Backend | Admin bookings list API + filters
Week 4 | Backend | Assign vehicle/driver API
Week 2 | Frontend | Web checkout: quote → hold → pay
Week 2 | Frontend | Admin bookings list screens
Week 4 | Frontend | Admin assign vehicle/driver UI

## Payments
Payments · payment · 5 backend / 1 frontend · 2/6 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 2 | Backend | Razorpay order + webhook (idempotent) | [6 empty] | Week 2 | Backend | Payments API spec
Week 2 | Backend | Token invoice + verify APIs | [6 empty] | Week 2 | Backend | Payment Nest stub
Week 4 | Backend | Refund path for cancel before handover
Week 2 | Frontend | Checkout pay + success poll UI

## Subscription
Subscription · booking · 3 backend / 1 frontend · 1/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Later | Backend | Plans + tenure booking APIs | [6 empty] | Later | Backend | Subscription API spec
Later | Backend | Swap / early close policy APIs
Later | Frontend | Subscription plans + checkout UI

## Airport
Airport · booking · 3 backend / 1 frontend · 1/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 4 | Backend | Airport / one-way rate table APIs | [6 empty] | Week 4 | Backend | Airport / outstation API spec
Later | Backend | Tour package APIs
Week 4 | Frontend | Airport / one-way search options UI

## KYC
KYC · document · 4 backend / 2 frontend · 2/6 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 3 | Backend | Upload + admin approve/reject APIs | [6 empty] | Week 3 | Backend | KYC API spec
Week 3 | Backend | Gate booking on AWAITING_KYC | [6 empty] | Week 3 | Backend | Document Nest stub
Week 3 | Frontend | Customer KYC upload UI
Week 3 | Frontend | Admin KYC review screens

## E-sign
E-sign · document · 4 backend / 1 frontend · 1/5 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 3 | Backend | Agreement PDF from booking snapshot | [6 empty] | Week 3 | Backend | E-sign API spec
Week 3 | Backend | Leegality send + webhook
Week 3 | Backend | Advance to CONFIRMED after sign
Week 3 | Frontend | Customer sign / status page

## Fleet
Fleet · fleet · 4 backend / 1 frontend · 2/5 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 1 | Backend | City, Branch, Vehicle APIs | [6 empty] | Week 1 | Backend | Fleet API spec
Week 4 | Backend | Assign vehicle to confirmed booking API | [6 empty] | Week 1 | Backend | Fleet Nest stub
Week 1 | Frontend | Admin cars + vehicles CRUD screens

## Workshop
Workshop · fleet · 3 backend / 1 frontend · 1/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Later | Backend | Jobs + workshop calendar APIs | [6 empty] | Later | Backend | Workshop API spec
Later | Backend | Write AvailabilityBlock on schedule
Later | Frontend | Admin workshop screens

## Handover
Handover · fleet · 3 backend / 1 frontend · 1/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 4 | Backend | Handover API: odometer + photos | [6 empty] | Week 4 | Backend | Handover API spec
Week 4 | Backend | Return + close booking API
Week 4 | Frontend | Admin handover / return screens

## Drivers
Drivers · fleet · 2 backend / 1 frontend · 1/3 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 4 | Backend | Driver roster + assign APIs | [6 empty] | Week 4 | Backend | Drivers API spec
Week 4 | Frontend | Admin driver roster screens

## Partners
Partners · partner · 3 backend / 1 frontend · 1/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Later | Backend | Partner cars + commission ledger APIs | [6 empty] | Later | Backend | Partners API spec
Later | Backend | Settlements APIs (no partner portal)
Later | Frontend | Admin partner + settlement screens

## Admin
Admin · platform, fleet · 3 backend / 4 frontend · 1/7 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 4 | Backend | Dashboard KPI APIs | [6 empty] | Week 1 | Backend | Admin / multi-city spec
Week 4 | Backend | City / branch scoped RBAC on APIs
Week 1 | Frontend | Admin app shell + nav
Week 1 | Frontend | Staff, cars, vehicles screens
Week 4 | Frontend | Dashboard KPI screens
Week 4 | Frontend | City / branch scoped nav + filters

## Finance
Finance · platform · 2 backend / 1 frontend · 1/3 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Later | Backend | Revenue / deposits / GST report APIs | [6 empty] | Later | Backend | Finance API spec
Later | Frontend | Admin finance report screens

## Offers
Offers · platform · 3 backend / 2 frontend · 1/5 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 2 | Backend | Flat / percent offer code APIs | [6 empty] | Week 2 | Backend | Offers API spec
Later | Backend | Wallet + loyalty APIs
Week 2 | Frontend | Checkout apply offer code UI
Week 2 | Frontend | Admin offers screens

## Reviews
Reviews · platform · 2 backend / 1 frontend · 1/3 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Later | Backend | Review invite + ticket APIs | [6 empty] | Later | Backend | Reviews API spec
Later | Frontend | Post-trip review + support UI

## Notify
Notify · notification · 4 backend / 0 frontend · 2/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 1 | Backend | OTP email (port Gmail OAuth) | [6 empty] | Week 1 | Backend | Notifications API spec
Week 3 | Backend | Booking confirmation HTML email | [6 empty] | Week 1 | Backend | Notification Nest stub

## CRM
CRM · platform · 3 backend / 1 frontend · 1/4 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Week 3 | Backend | Zoho form webhook → lead | [6 empty] | Week 3 | Backend | CRM API spec
Week 4 | Backend | Contact form → CRM lead API
Week 4 | Frontend | Admin leads list screens

## Mobile
Mobile · apps/mobile · 0 backend / 2 frontend · 1/2 done
Each card is Backend (API/service) or Frontend (web/admin/mobile).
Not started |  |  | In progress |  |  | Under review |  |  | Completed
Week | Layer | Task | Week | Layer | Task | Week | Layer | Task | Week | Layer | Task
Later | Frontend | Expo app: search, book, track | [6 empty] | Later | Frontend | Mobile spec