## Legend
Dream-Drive MS — functionality tracker
Greenfield rebuild at dream-drive-MS (NestJS API :4000 + Next.js web/admin + Expo). Live product still in client-main/backend. Snapshot date: 2026-08-31.
How to read status
Status | Meaning
Done | Coded and usable (API + persistence). May still need production keys or UI polish.
In Progress | Partial: endpoint or screen exists but validations, UI, or edge cases are incomplete.
Under Review | Implemented with mock/fallback (Razorpay, Leegality, Gmail, Firebase). Needs staging verification.
Not Started | Not built in this repo yet (or explicitly out of scope).
Out of scope (confirmed)
Delivery / pickup executive operations
Partner self-service portal (admin manages partners)
Stack
Next.js 15 web :3000 (ported marketing site + new /fleet checkout path) · Next.js admin :3001 · NestJS API :4000 (identity, catalog, booking, payment, document, fleet, partner, notify, platform) · worker HOLD sweeper · socket :4010 · PostgreSQL/Prisma · Firebase Auth · Razorpay · Leegality · Zoho Forms · Expo mobile.
How to refresh this Google Sheet
File → Import → Upload Dream-Drive-Functionality-Tracker.xlsx → Import location: Replace spreadsheet. Each module is its own tab. Change Status via the dropdown; colours follow the cell.
Frontend developer tabs
FE Web Public, FE Web Account, FE Admin, FE Mobile — one row per page: route, how it should function, what exists today, APIs, status. Same dropdown: Done / In Progress / Under Review / Not Started.

## FE Web Account
Frontend — customer dashboard (apps/web)
Service: apps/web :3000 ¦ Priority: P0 ¦ Overall status: In Progress
Logged-in area. Guard all /account/* with AuthContext; redirect to /login. Customer can only see own data. Support must not impersonate. Nine pages are listed starting at row 5 (scroll to the top of this tab).
ID | Page | Route | How it should function | What exists today + APIs | Status | Priority | Gaps / next work
FE.A.01 | Account home | /account | Greeting, KYC status chip, shortcuts (bookings, KYC, invoices, tickets). Latest 5 bookings with status and track link. Edit name/phone. | Account.jsx shows name, KYC, booking list, KYC link, sign out. GET /v1/me/bookings. | In Progress | P0 | Profile edit form (PATCH /v1/me); nav to invoices/wallet/tickets.
FE.A.02 | My bookings | /account/bookings | Table/cards of all bookings: publicId, car, dates, amount, status. Filter by status. Click → detail or /track/:id. | List is inline on /account only. No dedicated route. | In Progress | P0 | Add /account/bookings page; empty state; cancel CTA with confirm.
FE.A.03 | Booking detail | /account/bookings/:id | Full timeline, vehicle/driver once assigned, pay remaining balance + deposit, links to KYC, agreement, invoices. Cancel until handover. | Uses /track/:bookingId. GET /v1/bookings/:id returns history, payments, KYC, agreements, driver, inspections. | In Progress | P0 | Pay balance/deposit buttons; cancel; download invoice.
FE.A.04 | KYC upload | /account/kyc | Upload Aadhaar, PAN, DL, selfie (pdf/jpg/png). Show status NOT_STARTED → SUBMITTED → APPROVED/REJECTED. Rejection reason + re-upload. After approve, prompt to sign agreement. | Kyc.jsx exists. POST /v1/kyc/submit, GET /v1/me/kyc. Uploads currently send a URL (no signed Cloudinary slot UI). | In Progress | P0 | Per-doc pickers; Cloudinary signed upload; rejection UX.
FE.A.05 | Agreements | /account/agreements | List agreements per booking. Open Leegality sign link. Download signed PDF when ready. Status DRAFT/SENT/SIGNED. | No page. GET /v1/me/agreements/:id is by id only (no list). | Not Started | P0 | Needs list endpoint or derive from booking.agreements; then build UI.
FE.A.06 | Invoices | /account/invoices | List tax invoices (number, date, amount, GST). Download/print. Link to booking. | No page. GET /v1/me/invoices returns Invoice + lines. No PDF yet. | Not Started | P0 | Build list + print view even if PDF comes later.
FE.A.07 | Wallet | /account/wallet | Show balance (INR) and last 50 txns. Later: pay part of token from wallet. | No page. GET /v1/me/wallet exists (balance 0, no debit at checkout). | Not Started | P2 | Read-only UI is enough until wallet pay is built.
FE.A.08 | Support tickets | /account/tickets | Open a ticket (subject, body, optional booking). List status. Reply thread. Cannot see internal notes. | No page. POST /v1/tickets exists. No customer list/reply UI. | Not Started | P2 | Add list + thread when GET /v1/me/tickets exists (today only POST).
FE.A.09 | Addresses / profile | /account (section) or /account/profile | Edit full name, phone (re-OTP later), default city, addresses. Once KYC approved, name matches KYC unless admin override. | PATCH /v1/me accepts fullName, phone, address JSON. No form. | Not Started | P0 | Simple profile form on account home is enough for MVP.
Counts | Done | In Progress | Under Review | Not Started

## FE Web Public
Frontend — public website (apps/web)
Service: apps/web :3000 ¦ Priority: P0–P1 ¦ Overall status: In Progress
Customer-facing marketing + booking path. New MS pages live under /fleet, /login, /checkout, /account, /track. Ported CRA pages still cover home, blogs, contact. Frontend owns UI, forms, Razorpay checkout widget, and calling NEXT_PUBLIC_API_URL (port 4000). No Prisma/Firebase Admin in the browser.
ID | Page | Route | How it should function | What exists today + APIs | Status | Priority | Gaps / next work
FE.W.01 | Home | / | Hero with city + dates search CTA that goes to /fleet. Show CMS banners, featured cars, how-it-works, testimonials, blogs teaser, WhatsApp/enquiry CTAs. Promo strips (sale/monsoon) come from GET /v1/public/banners, not hardcoded CSS. | Ported Home.jsx + Hero + MonsoonPromoBar (hardcoded). Does not call banners API. | In Progress | P1 | Wire banners/CMS; search form should land on /fleet with query params.
FE.W.02 | Fleet / search | /fleet (also /cars) | Filters: city, from/to, rental type (self-drive vs chauffeur), seats, fuel, transmission, price. Results show image, from-price, available flag. Unavailable cars greyed. Sort by price. Clicking a card opens car detail with the same dates. | Search.jsx on /fleet calls GET /v1/public/cities + /v1/public/search (city/dates/SELF_DRIVE only). /cars is still the old FleetCarousel. | In Progress | P0 | Add remaining filters; unify /cars vs /fleet; pass dates into detail.
FE.W.03 | Car detail + quote | /cars/:slug | Gallery, specs, city, from-price. Date/time + rental-type picker. Show blocked dates / availability. CTA creates a quote then navigates to /checkout/:quoteId. Guest can browse; checkout requires login. | CarDetail.jsx exists. GET /v1/public/cars/:slug and availability. Calendar of blocked dates is thin. | In Progress | P0 | POST /v1/quotes from this page; blocked-date calendar; pickup/drop branch.
FE.W.04 | Login | /login | Email/password (Firebase) and email OTP. On success: POST /v1/auth/sync, store Bearer token, redirect to /account or intended checkout URL. Show errors and OTP resend cooldown. | Login.jsx is a local demo: loginDev(email) only. AuthContext.jsx holds the token. | In Progress | P0 | Real Firebase Auth + OTP send/verify UI. Google social login later.
FE.W.05 | Checkout (quote review) | /checkout/:quoteId | Show frozen price, dates, car, deposit, offer-code field. Confirm creates booking (HOLD) then starts token payment. If quote expired, send back to car detail. Login gate if anonymous. | Checkout.jsx applies offer, POST /v1/bookings, POST /v1/payments/orders, mock-verifies, then success. No quote GET (uses id from URL only). | In Progress | P0 | Load quote details; login redirect; do not mock-verify when Razorpay keys exist.
FE.W.06 | Pay (Razorpay) | /checkout/pay | Open Razorpay Checkout with orderId, keyId, amount from POST /v1/payments/orders. On success call POST /v1/payments/verify, then poll GET /v1/payments/:id until SUCCESS (webhook is source of truth). Handle failure/cancel. | No /checkout/pay route. Checkout.jsx verifies immediately when order.mock is true. | Not Started | P0 | Add Razorpay.js checkout page; poll payment status; never trust client success alone.
FE.W.07 | Booking success | /checkout/success | Show public booking id, amount, next steps: KYC (self-drive) or wait for confirm (with-driver). Links to /account/kyc and /track/:id. | SuccessMs.jsx exists after mock pay. | In Progress | P0 | Poll payment; branch copy for self-drive vs chauffeur.
FE.W.08 | Track booking | /track/:bookingId | Timeline: HOLD → payment → KYC → signature → confirmed → handover → ongoing → return → completed. Logged-in users use GET /v1/bookings/:id. Logged-out: id + phone OTP (later). Show driver name after assignment. | Track.jsx on /track/:bookingId. Old /order-tracking still exists. Guest OTP not built. | In Progress | P0 | Guest track; live status via socket :4010 optional.
FE.W.09 | Blogs | /blogs /blogs/:slug | List published posts with hero image, date, category. Detail shows body + comments (if enabled). SEO title/description from CMS. | AllBlogs / Blogspage ported (old context/Firestore). API GET /v1/public/blogs and /:slug exists. | In Progress | P1 | Point UI at platform API; drop Firestore blog context.
FE.W.10 | Contact / enquiry | /contact | Name, phone or email, city, message. Submit POST /v1/public/contact (creates CRM lead). Success toast. WhatsApp CTA can fire POST /v1/public/leads with source=whatsapp. | Ported Contact.jsx + WhatsAppPopup. May still hit old backend. | In Progress | P1 | Switch to API; track WhatsApp clicks as leads.
FE.W.11 | CMS / legal pages | /about /howitworks /termsandconditions /legal/:slug | Render published CmsPage by slug (title + body + meta). Admin can update without a deploy. | Static About, HowItWorks, TermsAndConditions components. GET /v1/public/pages/:slug exists unused. | In Progress | P1 | Drive these from CMS; add /legal/:slug.
FE.W.12 | Packages (airport / tours) | /packages | List published tour/airport packages with days, price, inclusions. Select → quote with product AIRPORT/TOUR. | No route in Container.jsx. GET /v1/public/packages is ready. | Not Started | P2 | Build listing + detail after daily booking path is stable.
FE.W.13 | Header, footer, global chrome | all public routes | Nav: Home, Fleet, Packages, Blogs, Contact, Login/Account. After login show name + KYC badge. City selector. Footer links to legal CMS pages. | Ported Header/Footer. AuthProvider wraps the app but header may not use it. | In Progress | P0 | Auth-aware nav; link Fleet to /fleet not old carousel.
FE.W.14 | Testimonials | /testimonials (and home module) | Published testimonials on home. Optional listing page. | Testimonial.jsx + TestimonialContext (old). No new API. | Not Started | P1 | Needs public testimonials API first, then wire home.
Counts | Done | In Progress | Under Review | Not Started

## FE Admin
Frontend — operations console (apps/admin :3001)
Service: apps/admin ¦ Priority: P0–P1 ¦ Overall status: In Progress
Staff-only Next.js app. Token in localStorage (dd_token). Sidebar Shell. Role-aware nav later (SUPER_ADMIN sees all). Call the same API :4000. Old Firestore admin still lives under apps/web /admin — do not extend it; migrate screens here.
ID | Page | Route | How it should function | What exists today + APIs | Status | Priority | Gaps / next work
FE.AD.01 | Admin login | /login | Staff email login (Firebase or dev token). Reject CUSTOMER role. Redirect to dashboard. | apps/admin/app/login/page.jsx exists. | In Progress | P0 | Block non-staff; show role; production Firebase.
FE.AD.02 | Dashboard | / | KPI cards: bookings, pending KYC, pending signatures, failed payments, today’s handovers, overdue returns, vehicles in workshop, revenue. Filter city + date. Status breakdown table. | app/page.jsx shows bookings, pending KYC, vehicles free, revenue, byStatus. GET /v1/admin/dashboard. | In Progress | P1 | Add remaining KPIs when API returns them; city filter.
FE.AD.03 | Bookings list | /bookings | Filter by status, city, dates, q. Columns: publicId, customer, car, dates, amount, status. Row click → detail. | app/bookings/page.jsx exists (list). | In Progress | P0 | Filters + pagination; status chips.
FE.AD.04 | Booking detail + ops | /bookings/[id] | Timeline, notes, flight number. Actions: change status, assign vehicle, assign driver, handover (odometer, fuel, photos), return (+ damages), generate/send agreement, mark signed, record offline pay. Show payments/KYC/inspections. | No [id] page. APIs: GET booking, PATCH, POST status/assign-vehicle/assign-driver, POST handover/return, agreements, offline pay. | Not Started | P0 | Highest-value admin screen after list. Build this next.
FE.AD.05 | Car models | /cars | CRUD models: name, slug, type, seats, fuel, transmission, city, published, featured, images, pricing rules (daily/hourly/deposit). | app/cars/page.jsx + GET/POST/PATCH /v1/admin/car-models and pricing-rules. | In Progress | P0 | Image manager; inline pricing editor.
FE.AD.06 | Vehicles | /vehicles | CRUD physical cars: registration, model, branch, status, odometer, partner. Expiry alerts for RC/insurance/PUC. | app/vehicles/page.jsx + /v1/admin/vehicles. GET expiries exists, no document CRUD UI. | In Progress | P0 | Status change; branch transfer; document expiry panel.
FE.AD.07 | Availability calendar | /availability | Per city/branch, see vehicles blocked by bookings, HOLD, maintenance. Staff can add a manual block. | No page. Availability is computed in catalog search. | Not Started | P1 | Read-only calendar first; manual block later.
FE.AD.08 | Customers | /customers | Search users. View profile, roles, bookings. SUPER_ADMIN: set roles, disable. No impersonation. | app/customers/page.jsx + GET /v1/admin/users, PATCH roles, POST disable. | In Progress | P0 | Customer drawer with bookings + KYC; role editor.
FE.AD.09 | KYC queue | /kyc | Queue SUBMITTED/UNDER_REVIEW. Open docs. Approve/reject with notes. Decision advances self-drive booking. | app/kyc/page.jsx + GET /v1/admin/kyc, POST .../decision. | In Progress | P0 | Doc viewer; reject reason required.
FE.AD.10 | Agreements | /agreements | List envelopes. Generate PDF, send Leegality, mark signed (waiver), void/re-issue later. | No admin page. APIs: generate, send-leegality, mark-signed. | Not Started | P0 | Can also live as actions on booking detail for MVP.
FE.AD.11 | Payments / invoices / deposits | /payments /invoices /deposits | List payments. Record offline cash/UPI. Refund (finance). Capture/release deposit. Show invoice numbers. | app/payments/page.jsx only. Refund/deposit/offline APIs exist without dedicated UI. | In Progress | P0 | Add refund + offline + deposit actions; invoices tab.
FE.AD.12 | Drivers | /drivers | CRUD chauffeurs, branch, active flag. Show current assignment. Leave calendar later. | app/drivers/page.jsx + driver CRUD. Assign happens on booking. | In Progress | P1 | Documents/DL expiry; availability.
FE.AD.13 | Maintenance | /maintenance | Create workshop jobs with dates → blocks availability. Complete job returns vehicle AVAILABLE. Parts/cost later. | No Shell link. POST /v1/admin/maintenance-jobs exists. | Not Started | P2 | Simple list + create is enough after booking path.
FE.AD.14 | Handover / inspections | /inspections or booking detail | Start handover: odometer, fuel, photos. Start return: same + damage lines (amount). Completes booking and posts partner ledger. | No page. POST /v1/admin/bookings/:id/handover and /return. | Not Started | P1 | Ship as booking-detail actions rather than a separate app.
FE.AD.15 | Partners + ledger + settlements | /partners /partners/[id]/ledger /settlements | CRUD partners, commission %. Ledger of trip earnings. Generate settlement period, mark paid with UTR. No partner login. | app/partners/page.jsx list. Ledger/settlement APIs exist, no UI. | In Progress | P2 | Partner detail + generate/mark-paid.
FE.AD.16 | Cities, branches, staff | /cities /branches /staff | CRUD cities/branches. Assign StaffScope (user + city + branch). City/branch switcher in the shell. | No pages. City/branch APIs exist. StaffScope assign API missing. | Not Started | P1 | Cities/branches UI can ship before staff-scope API.
FE.AD.17 | Offers | /offers | Create percent/flat codes with date window and max redemptions. Freeze abusive codes later. | app/offers/page.jsx + GET/POST /v1/admin/offers. | In Progress | P1 | Disable/freeze; city/product limits when API supports them.
FE.AD.18 | CMS, banners, blogs, media | /cms /blogs /banners /media | Edit pages by slug, banners (image, link, dates), blogs, media library. Publish/unpublish. | app/cms/page.jsx + CMS/banner APIs. No blogs/media screens in admin app. | In Progress | P1 | Banners + blogs editors; do not grow apps/web/Admin/*.
FE.AD.19 | Leads CRM | /leads | Pipeline NEW → CONTACTED → QUALIFIED → BOOKED/LOST. Notes. Convert to quote later. | app/leads/page.jsx + list/status/notes APIs. Convert not built. | In Progress | P1 | Kanban or status dropdown; convert when API exists.
FE.AD.20 | Tickets & reviews | /tickets /reviews | Ticket queue: assign, reply, internal notes. Reviews: publish/hide. | No Shell links. GET /v1/admin/tickets and /reviews exist. No PATCH moderate. | Not Started | P2 | List views first; moderate when PATCH exists.
FE.AD.21 | Reports | /reports /reports/revenue /reports/gst | Date-range revenue, bookings, GST. Export CSV later. Finance + SUPER_ADMIN. | app/reports/page.jsx + GET /v1/admin/reports/:kind (revenue or gst). | In Progress | P2 | Date filters; CSV download.
FE.AD.22 | Notification log + templates | /notifications | Delivery log. Edit email templates by key. Resend later. | No page. GET logs + PUT templates exist. | Not Started | P1 | Simple table + template editor.
Counts | Done | In Progress | Under Review | Not Started

## FE Mobile
Frontend — customer Expo app (apps/mobile)
Service: apps/mobile ¦ Priority: P2 ¦ Overall status: In Progress
Same /v1 APIs as web. Do not build full navigation until web checkout + KYC + pay work. Current App.tsx is a single-screen prototype.
ID | Page | Route | How it should function | What exists today + APIs | Status | Priority | Gaps / next work
FE.M.01 | Splash / force-update | screen 1 | Brand splash. If app version < min, block with store link. | Not built. | Not Started | P2 | Needs min-version from API or remote config.
FE.M.02 | Login / OTP | screen 2 | Email OTP or Firebase phone/email. Store token. POST /v1/auth/sync. POST /v1/me/devices for FCM. | Dev token only (Bearer dev:email) on App.tsx. | Not Started | P2 | No OTP UI.
FE.M.03 | Home + search | screens 3–4 | City + dates + type. Results from GET /v1/public/search. | App.tsx lists cars from search on load, no filters. | In Progress | P2 | Filters, pull-to-refresh, empty state.
FE.M.04 | Car detail | screen 5 | Gallery, availability calendar, quote CTA. | Not built (name + price only on list). | Not Started | P2
FE.M.05 | Checkout + Razorpay | screens 6–7 | Quote → booking → Razorpay native checkout → verify/poll. | Not built. | Not Started | P2 | After web Razorpay path is proven.
FE.M.06 | KYC + agreement | screen 8 | Upload docs (camera/gallery). Open Leegality in-app browser. | Not built. | Not Started | P2
FE.M.07 | Bookings + tracking | screens 9–10 | List + timeline. Deep link dreamdrive://bookings/:id. | App.tsx shows publicId + status after dev login. | In Progress | P2 | Detail timeline; push open.
FE.M.08 | Profile, tickets, notifications | screens 11–13 | Profile, support ticket, in-app notification list. | Not built. | Not Started | P2
Counts | Done | In Progress | Under Review | Not Started

## 00 Summary
Dream-Drive MS — module + frontend summary
Change Status on each module tab. Counts below use COUNTIF against that tab. Overall status is the current engineering judgement for the module as a whole.
# | Module | Service | Priority | Overall status | Done | In Progress | Under Review | Not Started | Total items | % Done | Notes
1 | FE Web Account | apps/web :3000 | P0 | In Progress | [6 empty] | Logged-in area. Guard all /account/* with AuthContext; redirect to /login. Customer can only see own data. Support must not impersonate. Nine pages are listed starting at row 5 (scroll to the top of this tab).
2 | FE Web Public | apps/web :3000 | P0–P1 | In Progress | [6 empty] | Customer-facing marketing + booking path. New MS pages live under /fleet, /login, /checkout, /account, /track. Ported CRA pages still cover home, blogs, contact. Frontend owns UI, forms, Razorpay checkout widget, and calling NEXT_PUBLIC_API_URL (port 4000). No Prisma/Firebase Admin in the browser.
3 | FE Admin | apps/admin | P0–P1 | In Progress | [6 empty] | Staff-only Next.js app. Token in localStorage (dd_token). Sidebar Shell. Role-aware nav later (SUPER_ADMIN sees all). Call the same API :4000. Old Firestore admin still lives under apps/web /admin — do not extend it; migrate screens here.
4 | FE Mobile | apps/mobile | P2 | In Progress | [6 empty] | Same /v1 APIs as web. Do not build full navigation until web checkout + KYC + pay work. Current App.tsx is a single-screen prototype.
5 | 01 Auth & Security | identity (apps/api) | P0 | In Progress | [6 empty] | Firebase + Postgres user sync, OTP, roles, and audit exist. OTP is in-memory (not Redis). Google login and last-super-admin lock are not built. Staff city/branch scope is stored but not fully enforced on every list.
6 | 02 Public CMS | platform + apps/web | P1 | In Progress | [6 empty] | Ported marketing site still runs in Next.js (home, blogs, monsoon bar). New CMS APIs exist for pages, banners, blogs, contact. Admin CMS page is a first version. Testimonials/comments still largely on the old UI.
7 | 03 Customer Dashboard | identity + booking + payment + document + web | P0 | In Progress | [6 empty] | Logged-in /account lists bookings and KYC status. APIs exist for invoices, wallet, tickets, agreements-by-id. Dedicated screens for invoices/wallet/tickets/agreements are not built yet.
8 | 04 Search & Availability | catalog | P0 | In Progress | [6 empty] | Public search, car detail, availability, pricing CRUD, HOLD reserve/release/confirm, and the worker HOLD sweeper are implemented. Search UI is /fleet. Seasonal pricing and a hard DB lock against double-book are still open.
9 | 05 Booking Engine | booking | P0 | In Progress | [6 empty] | Quote → HOLD → pay → KYC → signature → CONFIRMED path is coded, with admin assign vehicle/driver and cancel. Self-drive vs with-driver branch after payment. Chauffeur product rules, policy-based cancel, and admin-created bookings are incomplete.
10 | 06 Payments | payment | P0 | Under Review | [6 empty] | Razorpay order + verify + webhook + mock mode, invoices with flat 18% GST, offline pay, refund rows, deposit flags. Live Razorpay, real refunds, state-wise GST, and deposit authorize/capture need review in staging.
11 | 07 Subscription | booking + catalog | P2 | In Progress | [6 empty] | Data model + POST /v1/subscriptions creates a SUBSCRIPTION booking from a plan. No public plans API, swap, pause, or recurring invoices. After-MVP.
12 | 08 Airport & Packages | booking | P1–P2 | In Progress | [6 empty] | Tour packages and city-pair one-way rates have APIs. Quote accepts all RentalType values but pricing is still daily/hourly rules only — no terminal wait slabs, night charges, or driver allowance.
13 | 09 KYC & Documents | document | P0 | In Progress | [6 empty] | Customer submit + admin approve/reject advances self-drive bookings. Zoho webhook creates a KYC case. Uploads do not issue signed Cloudinary slots. Aadhaar hashing, DL expiry rules, and 12-month reuse are not built.
14 | 10 Agreement & eSign | document | P0 | Under Review | [6 empty] | HTML template render + send envelope (mock without LEEGALITY_API_KEY) + webhook/manual mark-signed advances booking to CONFIRMED. Not a real PDF yet. Vendor integration needs staging review.
15 | 11 Fleet | fleet | P0 | In Progress | [6 empty] | Cities, branches, vehicles CRUD and expiry read are live. Vehicle documents (RC/insurance/PUC) have a table but no admin CRUD. Assignment does not yet block on insurance dates.
16 | 12 Maintenance | fleet | P2 | In Progress | [6 empty] | Creating a maintenance job writes an availability block so search will not sell that car. Complete-job, parts, workshop CRUD, and admin UI are not built. After-MVP.
17 | 13 Handover & Return | fleet | P1 | In Progress | [6 empty] | Minimal handover/return APIs store odometer, fuel, photos, damages and move booking ONGOING → COMPLETED. Vehicle returns to drop branch and partner ledger is posted. Deposit auto-release and full damage matrix are not done. Delivery-exec app is out of scope.
18 | 14 Drivers | fleet | P1 | In Progress | [6 empty] | Driver CRUD + assign-to-booking work. Leave, availability calendar, DL validity, and single-assignment rules are not enforced. No driver marketplace (by design).
19 | 15 Partners | partner | P2 | In Progress | [6 empty] | Admin-only partner CRUD, commission rules, ledger on trip complete, settlement generate + mark-paid. No partner portal (confirmed exclusion). Open-damage hold and frozen-at-booking commission version still missing.
20 | 16 Admin & Multi-city | fleet + platform + apps/admin | P0–P1 | In Progress | [6 empty] | New ops console (port 3001) has dashboard, bookings, cars, vehicles, drivers, KYC, customers, payments, partners, leads, offers, CMS, reports. City/Branch exist on entities. StaffScope table exists but there is no assign-scope API or query filtering. Old admin UI still lives inside apps/web /admin.
21 | 17 Finance & Reports | platform + payment | P2 | In Progress | [6 empty] | Basic revenue + GST report endpoints and an admin reports page. No CSV export, deposit/partner reports, or Razorpay recon queue. GST is a flat 18% on invoice create.
22 | 18 Offers & Wallet | platform + payment + booking | P1–P2 | In Progress | [6 empty] | Coupon apply on quote is real (window, max redemptions, one per user). Admin can create offers. Wallet/loyalty rows are created at signup but earn/redeem/referral are not. P1 = coupons; P2 = wallet/loyalty.
23 | 19 Reviews & Support | platform | P2 | In Progress | [6 empty] | Customers can create a review (unpublished) and a ticket. Admin can list both. No moderate/publish, public car reviews, ticket assign/SLA, or customer ticket UI.
24 | 20 Notifications | notification + worker | P0 | Under Review | [6 empty] | Internal notify + templates + logs + retry cron. Gmail OAuth/app-password when env is set; otherwise console mock. OTP and booking_confirmed are wired. SMS/WhatsApp later. Staging review once Gmail env is present.
25 | 21 CRM & Leads | platform | P1 | In Progress | [6 empty] | Contact and public lead APIs + admin pipeline (NEW→LOST) + notes. Convert-to-booking and 7-day dedupe are not built. Admin /leads page exists.
26 | 22 Mobile | apps/mobile | P2 | In Progress | [6 empty] | Expo package with a single-screen prototype: dev sign-in, public car list, my bookings. No OTP, checkout, Razorpay, KYC, tracking, tickets, or store build. Spec: do not invest until web checkout is stable.
TOTAL
Status rollup (all items)
Status | Count
Done
In Progress
Under Review
Not Started

## 01 Auth & Security
01 — Auth & security baseline
Service: identity (apps/api) ¦ Priority: P0 ¦ Overall status: In Progress
Firebase + Postgres user sync, OTP, roles, and audit exist. OTP is in-memory (not Redis). Google login and last-super-admin lock are not built. Staff city/branch scope is stored but not fully enforced on every list.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
01.01 | Firebase ID token verification | Backend | API verifies Firebase ID tokens with firebase-admin when FIREBASE_PROJECT_ID is set; otherwise token resolve returns null. | apps/api/src/auth.middleware.ts → verifyFirebase | Under Review | P0 | Needs staging check with live Firebase project keys.
01.02 | Dev auth bypass (local) | Backend | Bearer dev:email upserts a user and is allowed unless DEV_AUTH_BYPASS=false. | auth.middleware.ts resolveUser | Done | P0 | Must stay off in production.
01.03 | Auth sync into PostgreSQL | Customer / Backend | POST /v1/auth/sync upserts User + CustomerProfile + CUSTOMER role + empty wallet/loyalty. | POST /v1/auth/sync · identity.service.ts upsertFromIdentity | Done | P0 | Gateway leftover service is unused; monolith API does this itself.
01.04 | Email OTP send | Customer | POST /v1/auth/otp/send issues a 5-min code (in-memory Map) and calls notification service. Dev returns devCode. | POST /v1/auth/otp/send | In Progress | P0 | Replace Map with Redis; production must not expose devCode.
01.05 | Email OTP verify | Customer | POST /v1/auth/otp/verify checks in-memory store. | POST /v1/auth/otp/verify | In Progress | P0 | No session mint beyond Firebase; OTP is email-verify helper only.
01.06 | OTP rate limit | Backend | 8 requests / 15 minutes per IP on /v1/auth/otp/send. | auth.middleware.ts rateLimitOtp | Done | P0 | Raise to documented 3/15 min if product wants stricter.
01.07 | Current user profile | Customer | GET /v1/me and PATCH /v1/me (name, phone, address JSON). | GET/PATCH /v1/me | Done | P0 | Phone change does not re-trigger OTP yet.
01.08 | FCM / device token register | Mobile / Web | POST /v1/me/devices stores DeviceToken. | POST /v1/me/devices | Done | P2 | Mobile app does not call this yet.
01.09 | Admin user search | Admin | GET /v1/admin/users?q= for SUPPORT/SALES/CITY_MANAGER/SUPER_ADMIN. | GET /v1/admin/users · admin /customers | Done | P0 | No pagination beyond simple query.
01.10 | Assign staff roles | Admin | PATCH /v1/admin/users/:id/roles (SUPER_ADMIN). | PATCH /v1/admin/users/:id/roles | Done | P0 | Last remaining SUPER_ADMIN cannot be removed — not coded.
01.11 | Disable user | Admin | POST /v1/admin/users/:id/disable. | POST /v1/admin/users/:id/disable | Done | P0
01.12 | Audit log | Admin | GET /v1/admin/audit. Writes happen on auth.sync, role change, disable, offline payment. | GET /v1/admin/audit · AuditLog model | In Progress | P0 | Not every privileged write is audited (refunds, KYC decision, status moves).
01.13 | RBAC helpers | Backend | requireRoles / requireStaff / assertInternal / assertOwnerOrStaff. SUPER_ADMIN bypasses role checks. | apps/api/src/lib/auth.ts | Done | P0 | StaffScope (city/branch) is not applied as a query filter.
01.14 | Public vs authed routes | Backend | Public: /v1/public/*, OTP, webhooks. Other /v1 requires Bearer. | auth.middleware.ts PUBLIC | Done | P0 | Internal routes live at /internal/* (not /v1/internal).
01.15 | Web login | Customer | New login page uses Firebase/dev token via AuthContext. | apps/web/src/ms/pages/Login.jsx · AuthContext.jsx | In Progress | P0 | Google social login not started.
01.16 | Admin login | Admin | apps/admin login stores dd_token and calls API. | apps/admin/app/login/page.jsx | In Progress | P0 | Uses same Bearer scheme; polish UX later.
01.17 | Google / social login | Customer | Documented as later; no provider wiring. | docs/modules/01-auth-security.md | Not Started | P2 | Add Firebase Google provider after email path is stable.
Counts | Done | In Progress | Under Review | Not Started

## 02 Public CMS
02 — Public website & CMS
Service: platform + apps/web ¦ Priority: P1 ¦ Overall status: In Progress
Ported marketing site still runs in Next.js (home, blogs, monsoon bar). New CMS APIs exist for pages, banners, blogs, contact. Admin CMS page is a first version. Testimonials/comments still largely on the old UI.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
02.01 | Marketing home | Customer | Ported Home + hero + why-us + fleet teaser + monsoon promo bar (still hardcoded CSS/content). | apps/web/src/components/home/Home.jsx · MonsoonPromoBar.jsx | In Progress | P1 | Drive strips/banners from GET /v1/public/banners.
02.02 | Public CMS pages | Customer | GET /v1/public/pages/:slug returns published CmsPage. | GET /v1/public/pages/:slug | Done | P1 | Web legal pages still static TermsAndConditions, not CMS-driven.
02.03 | Public banners | Customer | GET /v1/public/banners respects active + date window. | GET /v1/public/banners | Done | P1 | Home does not consume this API yet.
02.04 | Public blogs list/detail | Customer | GET /v1/public/blogs and /:slug. Old AllBlogs/Blogspage UI still present. | GET /v1/public/blogs · apps/web blogs components | In Progress | P1 | Point web blogs at platform API instead of Firestore context.
02.05 | Contact form → CRM lead | Customer | POST /v1/public/contact creates Lead + optional activity note. | POST /v1/public/contact | Done | P1 | Old Contact.jsx may still write the previous backend — switch to API.
02.06 | Admin CMS pages | Admin | GET/POST /v1/admin/cms upsert by slug. Admin /cms page exists. | CRUD /v1/admin/cms · apps/admin/app/cms/page.jsx | In Progress | P1 | No unpublish workflow beyond published flag; no media picker.
02.07 | Admin banners | Admin | GET/POST/PATCH /v1/admin/banners. | /v1/admin/banners | In Progress | P1 | No delete endpoint; admin UI may be combined into CMS page.
02.08 | Testimonials | Customer / Admin | Testimonial model in Prisma. Live UI uses old TestimonialContext (ported site). | schema Testimonial · apps/web Testimonial.jsx | Not Started | P1 | Add public + admin APIs and wire home.
02.09 | Blog comments | Customer | BlogComment on schema; public blog include comments. No POST comment API. | schema BlogComment | Not Started | P2 | Auth or moderation flag per spec.
02.10 | SEO / page metadata | Admin | PageMetadata model. Web has SeoDefaults.jsx on old site. | schema PageMetadata · SeoDefaults.jsx | In Progress | P1 | Admin metadata CRUD not on new API.
02.11 | WhatsApp / enquiry CTAs | Customer | Ported WhatsAppPopup + ContactPopup + Numberattach. | apps/web WhatsAppPopup · ContactPopup | In Progress | P1 | Clicks are not logged as CRM leads yet.
Counts | Done | In Progress | Under Review | Not Started

## 03 Customer Dashboard
03 — Customer accounts & web dashboard
Service: identity + booking + payment + document + web ¦ Priority: P0 ¦ Overall status: In Progress
Logged-in /account lists bookings and KYC status. APIs exist for invoices, wallet, tickets, agreements-by-id. Dedicated screens for invoices/wallet/tickets/agreements are not built yet.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
03.01 | Account home | Customer | /account shows name, KYC status, booking list with track links. | apps/web/src/ms/pages/Account.jsx · GET /v1/me/bookings | In Progress | P0 | No profile edit form, addresses UI, or invoices/wallet/tickets links.
03.02 | My bookings | Customer | GET /v1/me/bookings returns history + payments. | GET /v1/me/bookings | Done | P0 | No /account/bookings/[id] detail page (uses /track/:id).
03.03 | KYC from account | Customer | /account/kyc page + GET /v1/me/kyc. | Kyc.jsx · GET /v1/me/kyc | In Progress | P0 | See module 09 for upload/signed-URL gaps.
03.04 | Invoices download | Customer | GET /v1/me/invoices returns Invoice + lines. No account invoices screen. | GET /v1/me/invoices | In Progress | P0 | Build /account/invoices and PDF download.
03.05 | Wallet view | Customer | GET /v1/me/wallet upserts Wallet and returns txns. No UI. | GET /v1/me/wallet | In Progress | P2 | No credit/debit at checkout (module 18).
03.06 | Support tickets | Customer | POST /v1/tickets creates ticket + first message. No /account/tickets UI. | POST /v1/tickets | In Progress | P2 | No customer reply thread API beyond create.
03.07 | Agreements list/download | Customer | GET /v1/me/agreements/:id by id only — no list endpoint or page. | GET /v1/me/agreements/:id | Not Started | P0 | Add GET /v1/me/agreements and /account/agreements.
03.08 | No impersonation | Admin | No impersonate API (support is read-only by design). | docs/modules/03-customer-dashboard.md | Done | P0 | Keep it this way.
Counts | Done | In Progress | Under Review | Not Started

## 04 Search & Availability
04 — Search, discovery & availability
Service: catalog ¦ Priority: P0 ¦ Overall status: In Progress
Public search, car detail, availability, pricing CRUD, HOLD reserve/release/confirm, and the worker HOLD sweeper are implemented. Search UI is /fleet. Seasonal pricing and a hard DB lock against double-book are still open.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
04.01 | Public search | Customer | GET /v1/public/search filters city, seats, fuel, transmission, price, rentalType; returns from-price + available flag. | GET /v1/public/search · catalog.service.ts search | Done | P0 | No popularity sort; unpublished models excluded.
04.02 | Car detail by slug | Customer | GET /v1/public/cars/:slug with images, pricing, city. | GET /v1/public/cars/:slug · CarDetail.jsx | Done | P0 | Calendar of blocked dates is thin.
04.03 | Availability check | Customer | GET /v1/public/cars/:id/availability uses buffer hours and free-vehicle search. | GET /v1/public/cars/:id/availability | Done | P0
04.04 | Overlap + buffer + maintenance | Backend | vehicleBusy checks blocking booking statuses, AvailabilityBlock, MaintenanceJob. Buffer default 3h (BUFFER_HOURS). | catalog.service.ts vehicleBusy · findFreeVehicle | Done | P0 | No SELECT FOR UPDATE / serializable tx — race possible under concurrent checkout.
04.05 | HOLD reserve / release / confirm | Backend | Internal reserve creates HOLD:bookingId block; confirm renames to BOOKING:; release deletes. | POST /internal/availability/reserve¦release¦confirm | Done | P0 | Requires x-internal-token.
04.06 | HOLD sweeper | System | Worker cron every minute expires unpaid HOLD/AWAITING_PAYMENT and releases availability. | apps/worker hold-sweeper.job.ts · POST /internal/holds/expire | Done | P0 | HOLD_MINUTES env (default 15).
04.07 | Admin car models CRUD | Admin | GET/POST/PATCH/DELETE /v1/admin/car-models. Admin /cars page. | /v1/admin/car-models · apps/admin/app/cars | In Progress | P0 | Image management is create-time only.
04.08 | Pricing rules CRUD | Admin | GET/POST/PUT/DELETE /v1/admin/pricing-rules (daily/hourly/extraKm/deposit). | /v1/admin/pricing-rules | Done | P0 | No seasonal / date-window rules.
04.09 | Web search UI | Customer | /fleet uses new Search.jsx against the API (old /cars carousel still ported). | apps/web/src/ms/pages/Search.jsx | In Progress | P0 | Unify /cars vs /fleet; add sort chips.
04.10 | Seasonal / featured pricing | Admin | featured + displayOrder on CarModel only. | CarModel.featured | Not Started | P1 | Add date-ranged PricingRule.
Counts | Done | In Progress | Under Review | Not Started

## 05 Booking Engine
05 — Booking engine (all rental types)
Service: booking ¦ Priority: P0 ¦ Overall status: In Progress
Quote → HOLD → pay → KYC → signature → CONFIRMED path is coded, with admin assign vehicle/driver and cancel. Self-drive vs with-driver branch after payment. Chauffeur product rules, policy-based cancel, and admin-created bookings are incomplete.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
05.01 | Create quote (price freeze) | Customer | POST /v1/quotes computes days/hours from PricingRule, optional offer, TTL ~20 min. | POST /v1/quotes · booking.service.ts quote | Done | P0 | Airport wait/night/one-way extras not auto-added (see module 08).
05.02 | Apply offer on quote | Customer | POST /v1/quotes/:id/apply-offer validates window, cap, per-user. | POST /v1/quotes/:id/apply-offer | Done | P1 | No floor-price guard.
05.03 | Create booking from quote | Customer | POST /v1/bookings creates HOLD, reserves vehicle, moves to AWAITING_PAYMENT or cancels if no car. | POST /v1/bookings | Done | P0 | Quote TTL vs HOLD sweeper both apply.
05.04 | Get booking + history | Customer / Admin | GET /v1/bookings/:id includes history, extras, payments, KYC, agreements, driver, inspections. Owner or staff. | GET /v1/bookings/:id | Done | P0
05.05 | Cancel booking | Customer / Admin | Allowed until HANDOVER/ONGOING/COMPLETED. Releases availability. | POST /v1/bookings/:id/cancel | In Progress | P0 | No hours-before-start policy or auto refund.
05.06 | Lifecycle after payment | Backend | TOKEN/BALANCE success → SELF_DRIVE AWAITING_KYC else CONFIRMED. KYC approved → AWAITING_SIGNATURE. Signed → CONFIRMED. | internal /payment-captured /kyc-approved /agreement-signed | Done | P0 | With-driver skips KYC/sign by design.
05.07 | Admin bookings list / patch / status | Admin | GET /v1/admin/bookings, PATCH notes/dates/flight, POST status with confirm/release side effects. | /v1/admin/bookings* · apps/admin/app/bookings | In Progress | P0 | Date change does not re-quote or re-check availability.
05.08 | Assign vehicle | Admin | POST /v1/admin/bookings/:id/assign-vehicle. | POST .../assign-vehicle | In Progress | P0 | Does not re-validate insurance/status/overlap.
05.09 | Assign driver | Admin | POST assign-driver upserts DriverAssignment. | POST .../assign-driver | In Progress | P1 | No one-ongoing-trip or city-match validation.
05.10 | Status history | Backend | BookingStatusHistory written on create, pay, KYC, sign, cancel, expire, handover, return. | BookingStatusHistory | Done | P0
05.11 | Web checkout | Customer | /checkout/:quoteId applies offer, creates booking, mock-verifies Razorpay, goes to success. | Checkout.jsx | In Progress | P0 | No live Razorpay.js checkout when mock=false.
05.12 | Tracking page | Customer | /track/:bookingId new Track.jsx (old /order-tracking still exists). | Track.jsx | In Progress | P0 | Logged-out track-by-phone OTP not built.
05.13 | Realtime status | Customer | apps/socket BookingGateway on :4010. | apps/socket | In Progress | P1 | Web/admin do not subscribe yet.
05.14 | Admin create booking on behalf | Admin | No dedicated sales-create endpoint; would use customer quote APIs. | — | Not Started | P1 | Add POST /v1/admin/bookings with userId.
05.15 | NO_SHOW / grace | Admin | Status enum includes NO_SHOW; admin can POST status. No automatic grace job. | BookingStatus.NO_SHOW | Not Started | P1 | Add sweeper after start time.
Counts | Done | In Progress | Under Review | Not Started

## 06 Payments
06 — Payments, invoices & deposits
Service: payment ¦ Priority: P0 ¦ Overall status: Under Review
Razorpay order + verify + webhook + mock mode, invoices with flat 18% GST, offline pay, refund rows, deposit flags. Live Razorpay, real refunds, state-wise GST, and deposit authorize/capture need review in staging.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
06.01 | Create payment order (token/balance/deposit) | Customer | POST /v1/payments/orders uses booking amount. Mock order if no RAZORPAY_KEY_ID or PAYMENTS_MOCK=true. | POST /v1/payments/orders | Done | P0 | Amount is booking.amountPaise even for BALANCE (not remaining due).
06.02 | Client verify | Customer | POST /v1/payments/verify HMAC of order¦payment; mock marks SUCCESS. | POST /v1/payments/verify | Done | P0 | Webhook should remain source of truth in prod.
06.03 | Razorpay webhook | System | POST /v1/webhooks/razorpay signature check + idempotent eventId on captured/authorized. | POST /v1/webhooks/razorpay | Under Review | P0 | Test with Razorpay test-mode webhook secret.
06.04 | Invoice on success | Customer | Creates INV-YEAR-##### with GST 18% lines after SUCCESS. | payment.service.ts afterSuccess | In Progress | P1 | Not CGST/SGST vs IGST by state; no PDF.
06.05 | List my invoices | Customer | GET /v1/me/invoices. | GET /v1/me/invoices | Done | P0 | No customer UI yet.
06.06 | Offline cash/UPI | Admin | POST /v1/admin/payments/offline marks SUCCESS and runs afterSuccess + audit. | POST /v1/admin/payments/offline | Done | P1 | No branch-scoping of who can record.
06.07 | Refunds | Admin | POST /v1/admin/payments/:id/refund writes Refund row and payment status. Does not call Razorpay refund API. | POST /v1/admin/payments/:id/refund | In Progress | P1 | Wire Razorpay refunds + webhook.
06.08 | Security deposit capture/release | Admin | POST deposits/:id/capture¦release toggles held/released flags. | POST /v1/admin/deposits/:id/* | In Progress | P1 | No Razorpay authorize; no auto-release after return inspection.
06.09 | Wallet read | Customer | GET /v1/me/wallet. | GET /v1/me/wallet | In Progress | P2 | Cannot pay token from wallet.
06.10 | Admin payments UI | Admin | apps/admin/app/payments page. | apps/admin/app/payments/page.jsx | In Progress | P0 | Needs refund/deposit actions in UI.
06.11 | Razorpay settlement recon | Admin | No PayoutReconciliation flow. | — | Not Started | P2 | Finance mismatch queue.
Counts | Done | In Progress | Under Review | Not Started

## 07 Subscription
07 — Car subscription & long-term
Service: booking + catalog ¦ Priority: P2 ¦ Overall status: In Progress
Data model + POST /v1/subscriptions creates a SUBSCRIPTION booking from a plan. No public plans API, swap, pause, or recurring invoices. After-MVP.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
07.01 | Subscription plan table | Backend | SubscriptionPlan (months, price, carModel) in Prisma. | packages/database/prisma/schema.prisma SubscriptionPlan | Done | P2 | No admin CRUD API for plans.
07.02 | Start subscription | Customer | POST /v1/subscriptions quotes SUBSCRIPTION, overwrites amount to plan price, creates booking + Subscription row. | POST /v1/subscriptions | In Progress | P2 | Starts immediately; no handover-aligned start; needs available vehicle.
07.03 | Public plans listing | Customer | GET /v1/public/subscriptions/plans not implemented. | — | Not Started | P2
07.04 | Swap / early close | Admin | POST /v1/admin/subscriptions/:id/swap¦close not implemented. | — | Not Started | P2
07.05 | Monthly invoice / mandate | Finance | Spec says invoice-per-month; not built. | — | Not Started | P2 | Razorpay mandate later.
Counts | Done | In Progress | Under Review | Not Started

## 08 Airport & Packages
08 — Airport, outstation, one-way & tours
Service: booking ¦ Priority: P1–P2 ¦ Overall status: In Progress
Tour packages and city-pair one-way rates have APIs. Quote accepts all RentalType values but pricing is still daily/hourly rules only — no terminal wait slabs, night charges, or driver allowance.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
08.01 | Public tour packages | Customer | GET /v1/public/packages published TourPackage + TourDay. | GET /v1/public/packages | Done | P2 | No /packages web route.
08.02 | Admin packages CRUD | Admin | GET/POST/PATCH + POST delete /v1/admin/packages. | /v1/admin/packages | In Progress | P2 | No admin UI page; daysDetail not edited on create.
08.03 | City-pair one-way fee | Admin | GET/POST /v1/admin/city-pairs upserts CityPairRate. | /v1/admin/city-pairs | In Progress | P1 | Quote engine does not add oneWayPaise yet.
08.04 | Quote product types | Customer | POST /v1/quotes accepts SELF_DRIVE, WITH_DRIVER_*, AIRPORT, OUTSTATION, ONE_WAY, TOUR, SUBSCRIPTION via Prisma enum. | POST /v1/quotes rentalType | In Progress | P1 | WITH_DRIVER_LOCAL uses hourlyPaise; others use dailyPaise only.
08.05 | Flight number | Admin | adminPatch can set flightNumber. | PATCH /v1/admin/bookings/:id | In Progress | P1 | Customer checkout does not collect flight/terminal.
08.06 | Airport terminals & wait slabs | Admin | AirportTerminal model only — no API. | schema AirportTerminal | Not Started | P1 | Free wait minutes + night charges.
08.07 | Outstation driver allowance | Backend | Not in quote calculation. | — | Not Started | P1 | Auto-add per night.
08.08 | Web packages page | Customer | Not in Container.jsx routes. | — | Not Started | P2 | Add /packages.
Counts | Done | In Progress | Under Review | Not Started

## 09 KYC & Documents
09 — Legal KYC & documents
Service: document ¦ Priority: P0 ¦ Overall status: In Progress
Customer submit + admin approve/reject advances self-drive bookings. Zoho webhook creates a KYC case. Uploads do not issue signed Cloudinary slots. Aadhaar hashing, DL expiry rules, and 12-month reuse are not built.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
09.01 | Submit KYC case | Customer | POST /v1/kyc/submit creates KycCase SUBMITTED + KycDocument URLs; sets profile.kycStatus. | POST /v1/kyc/submit | Done | P0 | No MIME/size validation server-side.
09.02 | Signed upload slots | Customer | POST /v1/kyc/uploads echoes url/kind — does not mint Cloudinary/S3 signature. | POST /v1/kyc/uploads | In Progress | P0 | Issue signed upload; never accept arbitrary URLs in prod.
09.03 | My KYC | Customer | GET /v1/me/kyc with documents + zoho. | GET /v1/me/kyc · Kyc.jsx | Done | P0
09.04 | Admin KYC queue + decision | Admin | GET /v1/admin/kyc; POST decision APPROVED/REJECTED; on approve calls booking kyc-approved. | /v1/admin/kyc · apps/admin/app/kyc | Done | P0 | No UNDER_REVIEW state transition or request-reupload per doc.
09.05 | Zoho Forms webhook | System | POST /v1/webhooks/zoho-form upserts user by email, attaches latest awaiting booking, stores raw ZohoSubmission. | POST /v1/webhooks/zoho-form | In Progress | P0 | No HMAC; no attachment download to Cloudinary; weak booking match (email+status only).
09.06 | Aadhaar / PAN storage policy | Backend | Stores whatever URL/notes client sends. No hash+last4. | KycDocument | Not Started | P0 | Do not log raw Aadhaar.
09.07 | DL expiry vs drop-off | Backend | Not validated. | — | Not Started | P0
09.08 | Reusable KYC 12 months | Backend | New case created every submit. | — | Not Started | P1
09.09 | Web KYC UI | Customer | Kyc.jsx on /account/kyc. | apps/web/src/ms/pages/Kyc.jsx | In Progress | P0 | Complete doc kinds + rejection reason display.
Counts | Done | In Progress | Under Review | Not Started

## 10 Agreement & eSign
10 — Rental agreement & Leegality
Service: document ¦ Priority: P0 ¦ Overall status: Under Review
HTML template render + send envelope (mock without LEEGALITY_API_KEY) + webhook/manual mark-signed advances booking to CONFIRMED. Not a real PDF yet. Vendor integration needs staging review.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
10.01 | Generate agreement | Admin | POST /v1/agreements/generate renders HTML placeholders (publicId, customer, dates, amount). pdfUrl is html://… | POST /v1/agreements/generate | In Progress | P0 | Replace with PDFKit/HTML→PDF; vehicle + tariff + jurisdiction fields.
10.02 | Send to Leegality | Admin | POST /v1/agreements/:id/send-leegality creates SignatureEnvelope. Mock id if no API key; live POST is best-effort. | POST /v1/agreements/:id/send-leegality | Under Review | P0 | Complete real Leegality payload + invite email match.
10.03 | Leegality webhook | System | POST /v1/webhooks/leegality updates envelope/agreement; on SIGN calls agreement-signed. | POST /v1/webhooks/leegality | In Progress | P0 | Add signature/IP allowlist.
10.04 | Admin wet-ink / waiver | Admin | POST /v1/admin/agreements/:id/mark-signed treats as signed. | POST /v1/admin/agreements/:id/mark-signed | Done | P0 | No void/re-issue endpoint.
10.05 | Customer download | Customer | GET /v1/me/agreements/:id owner or staff. | GET /v1/me/agreements/:id | In Progress | P0 | No signed PDF file yet.
10.06 | Templates by city/product | Admin | AgreementTemplate matched by rentalType or null. No admin CRUD. | schema AgreementTemplate | In Progress | P1 | Add CRUD + city dimension.
10.07 | Void and re-issue | Admin | POST /v1/admin/agreements/:id/void not implemented. | — | Not Started | P1
Counts | Done | In Progress | Under Review | Not Started

## 11 Fleet
11 — Vehicle & fleet management
Service: fleet ¦ Priority: P0 ¦ Overall status: In Progress
Cities, branches, vehicles CRUD and expiry read are live. Vehicle documents (RC/insurance/PUC) have a table but no admin CRUD. Assignment does not yet block on insurance dates.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
11.01 | Public cities | Customer | GET /v1/public/cities for search. | GET /v1/public/cities | Done | P0
11.02 | City CRUD | Admin | GET/POST/PATCH/DELETE /v1/admin/cities. | /v1/admin/cities | Done | P0 | No admin cities page in Shell.
11.03 | Branch CRUD | Admin | GET/POST/PATCH/DELETE /v1/admin/branches?cityId= | /v1/admin/branches | Done | P0 | Same — API only in new admin.
11.04 | Vehicle CRUD | Admin | Full CRUD; list includes model, branch, partner. Status/branch/odometer/partner on patch. | /v1/admin/vehicles · apps/admin/app/vehicles | Done | P0 | Registration unique at DB; no transfer-job entity.
11.05 | Move vehicle between branches | Admin | PATCH vehicle.branchId (also drop-branch on return). | PATCH /v1/admin/vehicles/:id | In Progress | P1 | No POST transfer-branch with audit/task.
11.06 | Document expiry alerts | Admin | GET /v1/admin/vehicles/expiries — documents expiring in 30 days. | GET /v1/admin/vehicles/expiries | In Progress | P1 | No VehicleDocument create/update API.
11.07 | RC / insurance / PUC files | Admin | VehicleDocument model only. | schema VehicleDocument | Not Started | P1 | CRUD + insurance-covers-booking check before assign.
11.08 | Partner-owned vehicles | Admin | ownerType/partnerId on create/update. | createVehicle | Done | P2 | Contract-active check not enforced.
Counts | Done | In Progress | Under Review | Not Started

## 12 Maintenance
12 — Maintenance & workshop
Service: fleet ¦ Priority: P2 ¦ Overall status: In Progress
Creating a maintenance job writes an availability block so search will not sell that car. Complete-job, parts, workshop CRUD, and admin UI are not built. After-MVP.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
12.01 | Create maintenance job + block | Admin | POST /v1/admin/maintenance-jobs creates job and AvailabilityBlock reason MAINT:id. | POST /v1/admin/maintenance-jobs | Done | P2 | Does not stop overlap with ONGOING booking.
12.02 | List / delete jobs | Admin | GET + DELETE. Delete may leave the availability block behind. | GET/DELETE /v1/admin/maintenance-jobs | In Progress | P2 | Delete should release MAINT: block; PATCH missing.
12.03 | Complete job → AVAILABLE | Admin | POST .../complete not implemented. | — | Not Started | P2 | Require odometer + cost.
12.04 | Parts / labour | Admin | MaintenancePart model unused in API. | schema MaintenancePart | Not Started | P2
12.05 | Workshop master | Admin | Workshop model, no CRUD. | schema Workshop | Not Started | P2
12.06 | Admin maintenance screen | Admin | Not in admin Shell nav. | apps/admin/components/Shell.jsx | Not Started | P2
Counts | Done | In Progress | Under Review | Not Started

## 13 Handover & Return
13 — Handover & return inspection
Service: fleet ¦ Priority: P1 ¦ Overall status: In Progress
Minimal handover/return APIs store odometer, fuel, photos, damages and move booking ONGOING → COMPLETED. Vehicle returns to drop branch and partner ledger is posted. Deposit auto-release and full damage matrix are not done. Delivery-exec app is out of scope.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
13.01 | Handover inspection | Admin | POST /v1/admin/bookings/:id/handover creates Inspection HANDOVER + photos; booking ONGOING; vehicle ON_TRIP. | POST /v1/admin/bookings/:id/handover | Done | P1 | Does not require CONFIRMED + signed agreement.
13.02 | Return inspection | Admin | POST .../return creates RETURN inspection, optional damages, booking COMPLETED, vehicle AVAILABLE at dropBranchId, releases availability, posts partner ledger. | POST /v1/admin/bookings/:id/return | Done | P1 | No odometer >= handover check; skips RETURN_PENDING.
13.03 | Damage line items | Admin | Damages nested on return body → DamageCharge. | returnVehicle damages[] | In Progress | P1 | Does not create Payment EXTRA or block partner payout.
13.04 | Dedicated damage API | Admin | POST /v1/admin/inspections/:id/damages missing. | — | Not Started | P1
13.05 | Deposit release on closed return | Finance | Not triggered from fleet. | — | Not Started | P1 | Event to payment-service.
13.06 | Customer acknowledge checklist | Customer | Out of MVP; not built. | — | Not Started | P2
13.07 | Admin handover UI | Admin | No inspections page in Shell; can only call API. | — | In Progress | P1 | Add booking-detail actions.
Counts | Done | In Progress | Under Review | Not Started

## 14 Drivers
14 — Driver & chauffeur management
Service: fleet ¦ Priority: P1 ¦ Overall status: In Progress
Driver CRUD + assign-to-booking work. Leave, availability calendar, DL validity, and single-assignment rules are not enforced. No driver marketplace (by design).
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
14.01 | Driver CRUD | Admin | GET/POST/PATCH/DELETE /v1/admin/drivers. Admin /drivers page. | /v1/admin/drivers · apps/admin/app/drivers | Done | P1
14.02 | Assign to booking | Admin | POST assign-driver upserts DriverAssignment. Booking GET includes driver. | POST /v1/admin/bookings/:id/assign-driver | Done | P1 | Customer UI does not show driver after assign.
14.03 | Driver documents | Admin | DriverDocument included on list; no upload/CRUD. | schema DriverDocument | In Progress | P1 | DL valid-through-trip check.
14.04 | Leave / availability | Admin | DriverLeave model. GET /v1/admin/drivers/availability missing. | schema DriverLeave | Not Started | P1
14.05 | One ONGOING assignment | Backend | Not validated. | — | Not Started | P1
Counts | Done | In Progress | Under Review | Not Started

## 15 Partners
15 — Partners, commission & settlement
Service: partner ¦ Priority: P2 ¦ Overall status: In Progress
Admin-only partner CRUD, commission rules, ledger on trip complete, settlement generate + mark-paid. No partner portal (confirmed exclusion). Open-damage hold and frozen-at-booking commission version still missing.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
15.01 | Partner CRUD | Admin | GET/POST/PATCH/DELETE /v1/admin/partners. Admin /partners page. | /v1/admin/partners | Done | P2
15.02 | Commission rules | Admin | PUT /v1/admin/partners/:id/commission-rules replaces rules (% bps + flat). | PUT .../commission-rules | Done | P2 | Not snapshotted onto the booking at HOLD time.
15.03 | Ledger on trip complete | System | Return inspection calls /internal/ledger/trip-complete → TRIP_EARNING + COMMISSION. | POST /internal/ledger/trip-complete | Done | P2 | Skipped if vehicle has no partnerId.
15.04 | View ledger | Admin | GET /v1/admin/partners/:id/ledger. | GET .../ledger | Done | P2
15.05 | Generate settlement | Admin | POST /v1/admin/settlements/generate sums ledger in period; unique partner+period. | POST /v1/admin/settlements/generate | Done | P2 | Does not exclude open DamageCharge.
15.06 | Mark paid (UTR) | Admin | POST /v1/admin/settlements/:id/mark-paid. | POST .../mark-paid | In Progress | P2 | Bank account required-before-pay not enforced.
15.07 | Partner self-service portal | Partner | Explicitly out of scope — admin manages partners. | README Out of scope | Not Started | — | Do not build.
Counts | Done | In Progress | Under Review | Not Started

## 16 Admin & Multi-city
16 — Admin console, multi-city & branch ops
Service: fleet + platform + apps/admin ¦ Priority: P0–P1 ¦ Overall status: In Progress
New ops console (port 3001) has dashboard, bookings, cars, vehicles, drivers, KYC, customers, payments, partners, leads, offers, CMS, reports. City/Branch exist on entities. StaffScope table exists but there is no assign-scope API or query filtering. Old admin UI still lives inside apps/web /admin.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
16.01 | Admin app shell | Admin | Next.js apps/admin with sidebar nav + token gate. | apps/admin/components/Shell.jsx | In Progress | P0 | Missing cities/branches/staff/maintenance/inspections/tickets/notifications pages.
16.02 | Dashboard KPIs | Admin | GET /v1/admin/dashboard: bookings count, pending KYC, free vehicles, revenue, byStatus. | GET /v1/admin/dashboard · app/page.jsx | In Progress | P1 | Spec also wants today’s handovers, overdue returns, pending signatures, failed payments, workshop — not included.
16.03 | City + branch on every entity | Backend | City/Branch models; vehicles/drivers/car models/bookings reference them. | schema City Branch | Done | P0
16.04 | StaffScope assign | Admin | StaffScope model. PUT /v1/admin/staff/:id/scope not implemented. | schema StaffScope | Not Started | P1 | CITY_MANAGER / BRANCH_MANAGER filtering.
16.05 | Scope enforcement | Backend | Lists return all rows; SUPER_ADMIN bypass only on roles. | lib/auth.ts | Not Started | P1 | Filter bookings/vehicles by x-city-id / x-branch-id.
16.06 | Legacy web admin | Admin | Ported AdminLayout still at /admin on the public site (blogs, form entries, users, rides). | apps/web Admin/* | In Progress | P1 | Retire Firestore admin after cutover.
Counts | Done | In Progress | Under Review | Not Started

## 17 Finance & Reports
17 — Finance, accounting & reports
Service: platform + payment ¦ Priority: P2 ¦ Overall status: In Progress
Basic revenue + GST report endpoints and an admin reports page. No CSV export, deposit/partner reports, or Razorpay recon queue. GST is a flat 18% on invoice create.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
17.01 | Revenue report | Admin | GET /v1/admin/reports/:kind — non-gst kinds return SUCCESS payments + totalPaise. | GET /v1/admin/reports/revenue | In Progress | P2 | No date-range or city filter; take 500.
17.02 | GST report | Admin | kind=gst sums invoice amount + gstPaise. | GET /v1/admin/reports/gst | In Progress | P2 | Not a real GSTR pack.
17.03 | Bookings / deposits / partners reports | Admin | Documented routes not implemented as distinct kinds. | docs/api-routes.md | Not Started | P2
17.04 | CSV export + audit | Admin | Not implemented. | — | Not Started | P1 | P1 in sprint notes for basic CSV.
17.05 | Admin reports UI | Admin | apps/admin/app/reports/page.jsx. | apps/admin/app/reports | In Progress | P2
17.06 | Razorpay vs internal mismatch | Finance | Not built. | — | Not Started | P2
Counts | Done | In Progress | Under Review | Not Started

## 18 Offers & Wallet
18 — Offers, loyalty, referral & wallet
Service: platform + payment + booking ¦ Priority: P1–P2 ¦ Overall status: In Progress
Coupon apply on quote is real (window, max redemptions, one per user). Admin can create offers. Wallet/loyalty rows are created at signup but earn/redeem/referral are not. P1 = coupons; P2 = wallet/loyalty.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
18.01 | Admin offers CRUD (create/list) | Admin | GET/POST /v1/admin/offers (PERCENT/FLAT, dates, maxRedemptions). Admin /offers page. | /v1/admin/offers | In Progress | P1 | No PATCH freeze/disable; no city/product/min-days.
18.02 | Apply coupon on quote | Customer | Checkout can POST apply-offer; booking stores offerId + redemption. | POST /v1/quotes/:id/apply-offer | Done | P1 | No floor price.
18.03 | Wallet ledger | Customer | Wallet + WalletTxn models; GET wallet. Signup creates zero balance. | GET /v1/me/wallet · identity upsert | In Progress | P2 | No credit/debit/adjust API; cannot pay from wallet.
18.04 | Loyalty points | Customer | LoyaltyAccount created at signup. No earn on COMPLETED, no /v1/me/loyalty. | schema LoyaltyAccount | Not Started | P2
18.05 | Referral codes | Customer | Referral model. No POST /v1/me/referrals. | schema Referral | Not Started | P2 | Credit after referee COMPLETED.
Counts | Done | In Progress | Under Review | Not Started

## 19 Reviews & Support
19 — Reviews & customer support desk
Service: platform ¦ Priority: P2 ¦ Overall status: In Progress
Customers can create a review (unpublished) and a ticket. Admin can list both. No moderate/publish, public car reviews, ticket assign/SLA, or customer ticket UI.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
19.01 | Create review | Customer | POST /v1/reviews stored published=false. | POST /v1/reviews | In Progress | P2 | No completed-booking or one-per-booking check.
19.02 | Admin review list | Admin | GET /v1/admin/reviews. | GET /v1/admin/reviews | In Progress | P2 | No publish/hide PATCH; no admin page in Shell.
19.03 | Public reviews on car | Customer | GET /v1/public/cars/:id/reviews missing. | — | Not Started | P2
19.04 | Open support ticket | Customer | POST /v1/tickets with subject/body/bookingId. | POST /v1/tickets | Done | P2 | No /account/tickets UI.
19.05 | Admin ticket queue | Admin | GET /v1/admin/tickets includes messages. | GET /v1/admin/tickets | In Progress | P2 | No PATCH assign/status/internal notes/SLA; no Shell link.
Counts | Done | In Progress | Under Review | Not Started

## 20 Notifications
20 — Notification suite
Service: notification + worker ¦ Priority: P0 ¦ Overall status: Under Review
Internal notify + templates + logs + retry cron. Gmail OAuth/app-password when env is set; otherwise console mock. OTP and booking_confirmed are wired. SMS/WhatsApp later. Staging review once Gmail env is present.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
20.01 | Internal send | System | POST /internal/notify renders template {{vars}} and emails or mocks. | POST /internal/notify · notify.service.ts | Done | P0 | HTML is wrapped in <pre>.
20.02 | Gmail delivery | System | nodemailer Gmail OAuth2 or app password if GMAIL_USER set. | notify.service.ts deliver | Under Review | P0 | Confirm production Gmail OAuth (ported from live backend).
20.03 | OTP email | Customer | identity sendOtp → template otp. Failures swallowed so login still works in dev. | POST /v1/auth/otp/send | In Progress | P0 | Dev still returns devCode.
20.04 | Booking confirmation email | Customer | Sent on with-driver CONFIRMED and on agreement-signed. | booking.service.ts paymentCaptured / agreementSigned | In Progress | P0 | Port current HTML template; self-drive confirm only after sign.
20.05 | Templates admin | Admin | GET list + PUT /v1/admin/notification-templates/:key. | /v1/admin/notification-templates | Done | P1 | No admin UI.
20.06 | Delivery log | Admin | GET /v1/admin/notifications last 200. | GET /v1/admin/notifications | Done | P1 | PII masking not done.
20.07 | Retry failed | System | Worker every 5 min → /internal/notify/retry. Retry currently re-sends template key as subject/body. | NotifyRetryJob | In Progress | P1 | Store original body; 3x backoff.
20.08 | SMS / WhatsApp | Customer | Same template table, channel later. | — | Not Started | P2
Counts | Done | In Progress | Under Review | Not Started

## 21 CRM & Leads
21 — Leads, enquiries & sales CRM
Service: platform ¦ Priority: P1 ¦ Overall status: In Progress
Contact and public lead APIs + admin pipeline (NEW→LOST) + notes. Convert-to-booking and 7-day dedupe are not built. Admin /leads page exists.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
21.01 | Public lead capture | Customer | POST /v1/public/leads and contact→lead. | POST /v1/public/leads · POST /v1/public/contact | Done | P1 | Phone-or-email required is not strictly enforced (name only).
21.02 | Admin lead list | Admin | GET /v1/admin/leads with activities. Admin /leads. | GET /v1/admin/leads | Done | P1
21.03 | Pipeline status | Admin | PATCH /v1/admin/leads/:id status NEW¦CONTACTED¦QUALIFIED¦BOOKED¦LOST. | PATCH /v1/admin/leads/:id | Done | P1 | No owner assign / reminders.
21.04 | Lead notes | Admin | POST /v1/admin/leads/:id/notes. | POST .../notes | Done | P1
21.05 | Convert lead → quote/booking | Admin | POST /v1/admin/leads/:id/convert missing. | — | Not Started | P1 | Prefill city + dates.
21.06 | Dedupe 7 days | Backend | Not implemented. | — | Not Started | P1 | Match phone+email.
21.07 | WhatsApp click as source | Customer | Popup exists; not tracked as lead. | WhatsAppPopup.jsx | Not Started | P1
Counts | Done | In Progress | Under Review | Not Started

## 22 Mobile
22 — Customer mobile app (Expo)
Service: apps/mobile ¦ Priority: P2 ¦ Overall status: In Progress
Expo package with a single-screen prototype: dev sign-in, public car list, my bookings. No OTP, checkout, Razorpay, KYC, tracking, tickets, or store build. Spec: do not invest until web checkout is stable.
ID | Functionality | Actor | Implementation (what exists today) | Code / API | Status | Priority | Gaps / next work
22.01 | Expo app shell | Customer | App.tsx SafeArea list + dev:email login + GET search + GET my bookings. | apps/mobile/App.tsx | In Progress | P2 | Not a navigation stack / screens 1–13.
22.02 | Login / OTP | Customer | Uses Bearer dev:email only. | App.tsx | Not Started | P2 | Firebase Auth + OTP.
22.03 | Search / detail / checkout / pay | Customer | Cars listed read-only; no quote/checkout/Razorpay. | — | Not Started | P2 | Reuse /v1/*.
22.04 | KYC + Leegality + track | Customer | Not built. | — | Not Started | P2
22.05 | Push device token | Customer | API POST /v1/me/devices ready; app unused. | POST /v1/me/devices | Not Started | P2 | FCM.
22.06 | Store release (Play/App Store) | Ops | No EAS config / force-update. | apps/mobile/package.json | Not Started | P2 | After web path is stable.
Counts | Done | In Progress | Under Review | Not Started